## Sep 2023
Date | Build count | Build released | Defect Count | Defect ID | Defect name
Sep 1 - Sep 9 | 8 | Week 36 Week 36.1 Week 36.2 Week 36.3 Week 36.4 Week 36.5 Week 36.6 Week 36.7 | 13 | #185967063 | On moving the instantaneous range slider, a device associated to selected zone gets neglected.
|  |  |  | 185972567 | In the aggregated view export, data is not downloaded for errorcode and currentmode metrics.
|  |  |  | 185973013 | Issue in the data downloaded from aggregated view.
|  |  |  | 185972952 | Data mismatch in downloads screen errorcode metric and custom chart with errorcode metric.
|  |  |  | #185989110 | In model viewer screen, instantaneous range slider is seen for aggregated view
|  |  |  | 185997521 | UI issue in current angle summary chart size
|  |  |  | 185999399 | On switching between time intervals and "All" checkbox, got a typeerror
|  |  |  | 185997791 | In historical performance export, "ts" column can be hidden.
|  |  |  | 186000028 | In availability vs errors summary and availability impact summary exported file, timestamp is displayed in place of site name.
|  |  |  | 185997787 | Issue in site summary export
|  |  |  | 186000011 | Data mismatch in availability impact summary chart and its exported file.
|  |  |  | #186005821 | Realtime date is not loading for a single device
|  |  |  | #186005216 | Zones offline count issue
Sep 11 - Sep 15 | 7 | Week 37 Week 37.1 Week 37.2 Week 37.3 Week 37.4 Week 37.5 Prod V3.3 | 2 | #186012396 | In historical performance chart, data is repeated twice for same day.
|  |  |  | #186015877 | In downloads screen, timestamp is not displayed for some of the metrics.
Sep 18 - Sep 22 | 5 | Week 38 Week 38.1 Week 38.2 Week 38.3 Prod V3.3.1 | 2 | #186089369 | When searched with device id, its zoom in to the zone level.
|  |  |  | #186089433 | At portfolio level, a metric heatmap is seen in model viewer screen.
Sep 25 - Sep 29 | 3 | Week 39 Week 39.1 Week 39.2 | 4 | #186121669 | Change less 30 to past 30 min in zones communicating
|  |  |  | #186139209 | In Gamechange modes summary chart, one day time interval is not working as expected.
|  |  |  | #186139131 | Under the portfolio "All", VA113 site's data is not updated in Portfolio summary table.
|  |  |  | #186147296 | In realtime screen, got Typeerror cannot read properties of undefined on doing column based search.
Oct 03-Oct 06 | 5 | Week 40 Week 40.1 Week 40.2 Week 40.3 Prod V3.3.2 | 10 | #186168998 #186190414 | Logs are recorded for charts that are not present in the site overview screen. After creating a custom chart, the word "last/count" is getting added to the chart title.
|  |  |  | #186189637 | Issue in the exported file from gamechange error summary chart.
|  |  |  | #186177071 | FTC SunOPS logo should be changed in new user email template.
|  |  |  | #186176775 | Custom chart with "current mode" metric shows future time
|  |  |  | #186176642 | In a custom chart with Active power metric, the device count should be in kilo watt
|  |  |  | #186176601 | Y-axis title is overlapped with the device count in a custom chart with active power metric.
|  |  |  | #186190224 | If a user selects game change option and export/view it should be seen in the logs.
|  |  |  | #186197807 #186197742 | Log is not recorded in downloads screen for some scenarios. In modes summary chart, device count is getting doubled.
Oct 09 - Oct 13 | 4 | Week 41 Week 41.2 Week 41.3 Prod V3.3.3 | 11 | #186218607 | Issue in currentangle metric order displayed in downloads screen and model viewer screen.
|  |  |  | #186212631 | Unselected date is displayed in the instantaneous range slider.
|  |  |  | #186209856 | The log is not recorded, when an user switches between aggregated and instantaneous view in the model viewer.
|  |  |  | #186211932 | Issue in model viewer "positional accuracy" metric
|  |  |  | #186220861 | Issue in model viewer wind direction heatmap
|  |  |  | #186230537 | Issue with custom chart deletion and clone.
|  |  |  | #186241001 | Trackerangle and Targetangle values can be rounded off.
|  |  |  | #186240169 | In field validation alert for page title, page name should be renamed as page title.
|  |  |  | #186239447 | In manage charts screen, "Select date range" option can be removed from chart preview.
|  |  |  | #186238060 | Future time is displayed in the downloads screen
|  |  |  | #186246311 | Issue in realtime screen alerts column
Oct 16 - Oct 20 | 3 | Week 42 Week 42.1 Prod V3.3.4 | 6 | #186268930 | In the exported file with 5 mins interval, ten mins interval data is seen.
|  |  |  | #186261798 | In non-ftc tracker site, availability value is not same in site summary and historical performance chart.
|  |  |  | #186261076 | Got an "unhandled rejection" error on viewing the tracker availability metric in model viewer.
|  |  |  | #186261744 | Availability average is not loading for last 1 hour and last 6 hours
|  |  |  | #186300675 | Availability value is mismatched in zone summary and availability vs errors chart
|  |  |  | #186300438 | Positional accuracy data mismatch
Oct 23 - Oct27 | 1 | Week 43 | 11 | #186311894 | Issue in realtime search and filter options.
|  |  |  | #186341701 | Availability data mismatch in portfolio summary and historical performance chart.
|  |  |  | #186341163 | Font type/size of the modes in "availability vs errors" chart is not the same.
|  |  |  | #186340674 | Issue in tracker availability aggregated view
|  |  |  | #186340606 | Historical performance chart is not loading at RC level.
|  |  |  | #186348314 | Non ftc data is not included in availability impact summary chart.
|  |  |  | #186348269 | Issue in downloads screen goto option.
|  |  |  | #186347874 | Issue with time intervals in downloads screen.
|  |  |  | #186347822 | In downloads screen, 1 min option can be removed from time intervals dropdown for other metrics except inverter data.
|  |  |  | #186347805 | Standard charts are not loading for last 1 hour and 6 hours time intervals
|  |  |  | #186347761 | Change current to past 60 mins in "Trackers with errors" card
Oct 30 and Oct 31 | 2 | Week 44 Week 44.1 | 1 | #186370947 | Error count displayed in portfolio summary table and error count in availability vs errors differs.

## Nov 2023
Date | Build count | Build released | Defect Count | Defect ID | Defect name
Nov 1 - Nov 3 | 1 | Prod V3.3.5 | 1 | #186379354 | Device count value differs in "availability vs error" chart and "availability impact summary" chart.
Nov 6 - Nov 10 | 4 | Week 45 Week 45.1 Week 45.2 Prod V3.3.6 | 3 | #186423733 | In Depcom portfolio, VA113 site is repeated twice in availability vs errors summary chart.
|  |  |  | #186432262 | Device id issue in model viewer instantaneous view.
|  |  |  | #186441942 | At PF level, device count shows as zero in availability vs errors chart
Nov 13 - Nov 17 | 4 | Week 46 Week 46.1 Week 46.2 Prod V3.3.7 | 4 | #186493892 | On cloning a custom chart, alert for "chart title" field is not seen.
|  |  |  | #186493903 | The exported file should get downloaded in the name of respective metrics names.
|  |  |  | #186494055 | Got typeerror on selecting "VA113" from portfolio dropdown.
|  |  |  | #186502263 | Need a scroll bar in My dashboards pop-up list.
Nov 20 - Nov24 | 3 | Week 47 Week 47.1 Prod V3.3.8 | 12 | #186514262 | Tooltip in the "availability impact summary" and "availability vs errors" charts can be same.
|  |  |  | #186514401 | If the site reaches more than 99% availability, in the availability impact summary chart a text "This site has reached 99%" can be shown.
|  |  |  | #186516388 | Changes made in the "clone existing"/"edit existing" screen should not get updated until it is saved.
|  |  |  | #186515994 | Availability data mismatch in portfolio summary and historical performance chart.
|  |  |  | #186516266 | Metrics data are seen in the model viewer screen even if the zone is in idle state.
|  |  |  | #186525018 | Issues in manage charts screen.
|  |  |  | #186526833 | Issue in instantaneous range slider
|  |  |  | #186526538 | Device count discrepancy in "availability vs errors" chart at portfolio level and site level.
|  |  |  | #186534675 | Demo server: For last 7 days time interval, historical performance shows data for last 5 days.
|  |  |  | #186541928 | Future time issue is still seen in direct downloads option.
|  |  |  | #186540678 | Demo server: Realtime data is not loading.
|  |  |  | #186540913 | Data in active power summary chart is not matching with the "active power metric" data in downloads screen.
Nov27 - Nov30 | 3 | Week 48 Week 48.1 Prod V3.3.9 | 4 | #186565917 | Change current to past 60 mins in "Mode" card.
|  |  |  | #186579098 | Issue with x-vibration metric in downloads screen.
|  |  |  | #186578696 | In livestatus screen, realtime data is seen for devices that are in offline mode.
|  |  |  | #186587203 | Remove the extra space in the summary table.

## Dec 2023
Date | Build count | Build released | Defect Count | Defect ID | Defect name
Dec_01(Week 48) | - | - | - | - | -
Dec 04- Dec 08 | 4 | Week 49 Week 49.1 Week 49.2 Prod V3.4 | 12 | #186607833 | Issue in downloads screen
|  |  |  | #186626959 | On editing a custom chart got 500 error in the logs.
|  |  |  | #186627788 | Issue with downloads page URL shared
|  |  |  | #186628105 | Issue with shared custom chart page URL
|  |  |  | #186628542 | Got "request failed with status code 500" while importing custom metric.
|  |  |  | #186628348 | Restrict the file type to upload in the "import custom metric" screen
|  |  |  | #186628521 | "Loading metric data" alert is seen for long time on switching between the sites in the model viewer screen.
|  |  |  | #186628477 | Issue in VA28 site tracker availability metric heatmap value.
|  |  |  | #186628447 | UI issues in Import custom metric screen.
|  |  |  | #186634713 | Encoded metric type file upload - Entered labels are not reflected in the heatmap.
|  |  |  | #186634441 | When uploading a binary type metric file with empty values, it autofills the values to "NO".
|  |  |  | #186636060 | Invalid timestamp is seen in the exported custom metric file
Dec 11 - Dec15 | 7 | Week#50 Week#50_1 Week#50_2 Week#50_3 Week#50_4 Week#50_5 Prod V3.4.1 | 13 | #186654276 | Misalignment issue in metric type varying and metric type encoded screen.
|  |  |  | #186655393 | Custom metric heatmap persists even after closing it in the model viewer dropdown.
|  |  |  | #186655500 | Discrepancy in gamechange errors summary chart at portfolio and site level.
|  |  |  | #186670865 | After removing a custom chart from one page, all other custom charts associated with different pages are shown on this page.
|  |  |  | #186672507 | Multiple entries are recorded on switching between pages.
|  |  |  | #186672416 | Logs are recorded for charts that are not present in the site overview screen.
|  |  |  | #186672429 | Optimize multiple API calls for Site card, Mode card and zones communicating card.
|  |  |  | #186680435 | Unhandled rejection typeError is displayed when a site is selected from the portfolio.
|  |  |  | #186679577 | Add env details in logs
|  |  |  | #186681247 | Logs for charts "availability vs errors" and "availability impact summary" is recorded twice.
|  |  |  | #186688665 | Not able to upload any type of file in "import custom metric" screen.
|  |  |  | #186688526 | At device level, graph is not seen in the error summary chart.
|  |  |  | #186688283 | Issue with custom charts logs and current angle summary chart logs.
Dec 18- 22 | 4 | Week#51 Week#51_1 Week#51_2 Week#51_3 | 8 | #186700731 | In the alerts column filter option, same alert is repeated twice.
|  |  |  | #186701490 | For last 7 days time interval, it shows data for last 6 days in "view and downloads" options for some metrics.
|  |  |  | #186701080 | An alert is seen in filters applied pop-up whereas it is not seen in the alerts column filter options.
|  |  |  | #186701010 | In the filter section, a comma appears before the alert names.
|  |  |  | #186709314 | Row id is missing in livestatus screen for Apex site.
|  |  |  | #186707896 | Custom chart shows future time.
|  |  |  | #186707888 | Data discrepancy in downloads screen and custom chart with x-vibration metric.
|  |  |  | #186717064 | All trackers are unknown in VA30 site
Dec 25- Dec29 | 3 | Prod V3.4.2 Week#52 Week#52_1 | 11 | #186739383 | Error in loading cards and charts in the overview screen after changing the time interval.
|  |  |  | #186742345 | The way of displaying validation alert should be changed.
|  |  |  | #186742600 | Breadcrumbs at the header section can be hidden in the user analytics screen.
|  |  |  | #186742609 | UI issues in user analytics screen
|  |  |  | #186742242 | Issue in end date selection in user analytics
|  |  |  | #186742658 | Issue in select user dropdown options.
|  |  |  | #186747242 | Previous entered "Possible values" is displayed even after uploading different csv file.
|  |  |  | #186747260 | On adding possible values in encoded metric, at times color coding populates empty with no color.
|  |  |  | #186747951 | Page name is not updated in the url for user analytics screen
|  |  |  | #186747872 | UI issues in custom model overlay
|  |  |  | #186747803 | Need a validation check if same color is selected while uploading custom metrics

## Jan 2024
Date | Build count | Build released | Defect Count | Defect ID | Defect name
Jan 2 - Jan 5 | 2 | Week 1 Prod V3.4.3 | 11 | 186760623 | In shared charts screen, need an option to "select all" and "deselect all" checkboxes.
|  |  |  | 186784886 | Editing shared charts inputs should be restricted.
|  |  |  | 186784767 | Need a validation alert when existing custom chart is added again to the same dashboard page.
|  |  |  | 186784355 | After deleting a custom chart, it should not redirect to the dashboard screen.
|  |  |  | 186784235 | In VA113 site, historical performance chart shows future time.
|  |  |  | 186784218 | In Rock garden site, mode is not displayed in Mode summary card.
|  |  |  | 186778570 | Along with the alert for already existing charts, a small empty box appears.
|  |  |  | 186778505 | Got page unresponsive error after deleting a custom chart.
|  |  |  | 186777120 | The minimum and maximum values in the heatmap should be rounded off.
|  |  |  | 186767262 | Got failed to fetch realtime data alert in live status screen.
|  |  |  | #186785584 | Issues in shared charts screen.
Jan8 - Jan12 | 3 | Week 2 Week 2_1 Prod V3.4.4 | 10 | #186796391 | Issue in date time picker
|  |  |  | #186796380 | Instantaneous range slider shows unselected date's data.
|  |  |  | #186798149 | Issue with the time interval in the exported file for the last one hour data.
|  |  |  | #186805274 | Hide last one hour and last 6 hours option from date time picker.
|  |  |  | #186815723 | For last 12 hours, 1 day time interval option can be removed.
|  |  |  | #186815709 | In direct downloads, 1min options can be removed or disabled for other metrics except inverter data.
|  |  |  | #186825627 | Issue with Angle value and error value displayed in saved snapshot.
|  |  |  | #186824103 | Data mismatch between "direct downloads" and "view and downloads" options in the downloads screen.
|  |  |  | #186832619 | The error field is seen blank, when multiple errors occurred for the same device at a same time.
|  |  |  | #186832408 | Charts already added in the dashboard are not checked in the shared charts screen.
Jan 15 - Jan 19 | 5 | Week 3 Week 3_1 Week 3_2 Week 3_3 Prod V3.4.5 | 2 | #186868276 | In the live status snapshots screen, if the notes are too long, they are not fully visible and get cut off.
|  |  |  | #186875113 | In livestatus snapshot screen, header in the notes can be highlighted.
Jan 22 - Jan 26 | 1 | Week 4 | 1 | #186894532 | Got "user not registered" alert for incorrect password.
Jan 29 - Jan 31 | 2 | Week 5 Week 5_1 | 3 | #186942147 | Last two days time interval issue in custom charts.
|  |  |  | #186942071 | Page name in the url changes for custom charts.
|  |  |  | #186950825 | Issue with dashboard title in custom charts

## Feb 2024
Date | Build count | Build released | Defect Count | Defect ID | Defect name
Feb 1 - Feb 2 |  |  | 1 | #186960019 | UI issues in notification service
Feb 5 - Feb 9 | 2 | Week 6 Week 6_1 | 4 | #186999844 | Functionality issues in Notification service.
|  |  |  | #187009029 | The detailed view table in the No data summary shows multiple entries with the same timestamp.
|  |  |  | #187016455 | Issue summary for non-ftc tracker site is not seen.
|  |  |  | #187016448 | Issue in records count displayed in "No data summary" screen.
Feb 12 - Feb 16 | 2 | Week 7 Prod V3.4.6 | 4 | #187026827 | Custom charts export file's format can be same as the consolidated export format.
|  |  |  | #187026937 | Issue in "No data summary" screen.
|  |  |  | #187026864 | Issue with value type "Total RCs" in custom charts.
|  |  |  | #187043972 | Hide search bar at the header in the user analytics screen.
Feb 19 - Feb 23 | 1 | Week 8 | 5 | 187078078 | Energy insights: Issue in PDF format exports
|  |  |  | 187077971 | Issue in Power timeline data view
|  |  |  | 187078152 | UI issues in Energy insights screen.
|  |  |  | 187078585 | Energy insights: For last 7 days time stamp, showing as no data available for power time line and energy production.
|  |  |  | 187078240 | Data discrepancy in power timeline(inverter level) chart
Feb 26 - Feb 29 | 2 | Week 9 Week 9_1 | 3 | 187130104 | The "Issue" column is overlapping with the "Avg. duration" column in the issue summary table.
|  |  |  | 187130128 | In the detailed issue summary view, data for unselected dates and times is being displayed.
|  |  |  | 187130188 | The data displayed in the detailed issue summary table is not matching when compared to the data in BigQuery.

## March 2024
Date | Build count | Build released | Defect Count | Defect ID | Defect name
March 1 - March 2
March 4 - March 8 |  |  | 3 | 187181410 | Issue summary is blank when there's an alert without an end time within the selected time range.
|  |  |  | 187198325 | Start and end time selection issue.
|  |  |  | 187199731 | Timezone does not get updated when scope of impact is changed.
March 11 - March 15 | 3 | Week 11 Week 11_1 Prod v3.5.1 | 5 | 187209069 | Add a scroll bar to left sidebar.
|  |  |  | 187208697 | Need an option to edit/delete site maintenance logs entered.
|  |  |  | 187235724 | Selected date range data is not getting downloaded in the consolidated format downloads.
|  |  |  | 187235788 | "Stow direction and release stow settings" header is overlapping on the dropdown options of the above fields.
|  |  |  | 187236885 | For non-SUNOPS user accounts, the "Edit Charts" and "What's New" icons should not be displayed.
March 18 - March 22 | 5 | Week 12 Week 12_1 Week 12_2 Week 12_3 Week 12_4 Prod v3.5.2 | 8 | 187257937 | TypeError occurs when Availability value is Null for all dates in selected time range.
|  |  |  | 187258312 | Overview screen flickers and disappears in the non-sunops user account, which should not occur.
|  |  |  | 187256503 | The summary table displays the "wind speed" column, but the other options selected from the drop-down menu are not shown in the table.
|  |  |  | 187283580 | Upon selecting the energy production of a site from the portfolio level, it does not direct to the site level.
|  |  |  | 187285567 | The hail settings icon should be non-clickable when the user is at the zone or device level.
|  |  |  | 187285564 | SunOPS - Week#12_4 test build on QA server - 21-March 2024
|  |  |  | 187284797 | In energy production chart info button, tooltip for "power timeline" is seen.
|  |  |  | 187285133 | Add loader on form submission and include success message for Site creation.
Macrh 25 - March 29 | 4 | Week 13 Week 13_1 Week 13_2 Prod V3.6 | 3 | #187303172 | Not able to add a new user to an existing notification group(common)
|  |  |  | #187329276 | Error messages appear during site selection in the weather forecast summary card.
|  |  |  | #187336251 | Email and SMS content in actions tab is not auto-populating in notification service production server.

## April 2024
April 2024 Build and Defects List
No.of.Test builds | 11
No.of.Production builds | 4
Date | Build count | Builds released | Defect Count | Defect ID | Defect name
April 1 - April 5 |  |  | 6 | 187359990 | Energy Insights issues - Backlog
|  |  |  | 187368995 | On selecting the Depcom portfolio, it loads the error/mode summary chart with the "Game change" option selected.
|  |  |  | 187362076 | Throwing 404 error while navigating to the sunops url at portfolio level for c_techtonicstesting2@ftcsolar.com
|  |  |  | 187369348 | Drop down value(Zones, Trackers) in the detailed view at site level is not getting reset when it is reopened for the next time.
|  |  |  | 187376641 | "Detailed forecast for next 7 days" table formatting issues
|  |  |  | 187378253 | Display 'Retry in 5 Seconds' Message for Unavailable Weather Forecast Due to 500 Internal Server Error.
April 8 - April 12 | 5 | Week 15_1 Week 15_2 Week15_3 Week15_4 Prod V3.6.1 | 1 | 187404471 | Duplicate 'X-Content-Type-Options' headers with 'nosniff' Value
April 15 - April 19 | 4 | Week 16 Week 16_1 Prod V3.6.2 Prod V3.6.3 | 5 | 187431423 | Issues in timezone fix
|  |  |  | 187440144 | In standard charts, when switching between time intervals, any selections made in the legends should stay the same.
|  |  |  | 187446492 | Duplicate data points with "No data" at Site level.
|  |  |  | 187446449 | The data is shifted back by one hour in the wind speed summary chart.
|  |  |  | 187455822 | At site level, Time zone in the URL shows tz=utc instead of tz=site.
April 22 - April 26 | 5 | Week 17 Week 17_1 Week 17_2 Week 17_3 Prod V3.7 | 5 | 187482682 | TypeError issue while navigating Test server across multiple tabs
|  |  |  | 187498227 | Data issues at energy insights screen for last 6 hours.
|  |  |  | 187497889 | When switching between sites, an error message 'inverters not configured...' appears for the site with configured inverters.
|  |  |  | 187497754 | Remove active power summary chart from overview screen.
|  |  |  | 187497718 | At Nexamp portfolio, "No portfolio data " is not seen in issue summary report.
April 29 - April 30 | 1 | Week 18 | 1 | 187515444 | The download options for historical performance charts are not visible when the user is at the top of the page.
Week | Count of build mails received | Build mails not received
April 1 - April 5 | 0
April 8 - April 12 | 3 | Week 15_1 Prod V3.6.1
April 15 - April 19 | 3 | Prod V3.6.3
April 22 - April 26 | 4 | week 17_3
April 29 - April 30 | 1
No.of.builds | 11 | 4

## May 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name
May 1 - May 3 | 2 | Week18_1 Week18_2 | 2 | #187535615 | Displaying incorrect zones when switching between sites
|  |  |  | #187543041 | In the detailed view of "No site data", From and To time should not be clickable.
May 6 - May 10 | 2 | Week19 Week19_1 | 9 | 187551472 | The Modes summary chart shows data for auto mode, but the Historical Performance chart does not calculate positional accuracy.
|  |  |  | 187551406 | "Trackers with no data" is not seen at site level for the sites under Depcom portfolio
|  |  |  | 187551295 | Snapshot name text size should be restricted or formatted.
|  |  |  | 187561904 | Map is not loading in hail settings screen
|  |  |  | 187559038 | Detailed forecast table overlaps on zone summary table
|  |  |  | 187576216 | Discrepancy in actual energy and expected energy displayed
|  |  |  | 187575693 | 404 error on reloading the page.
|  |  |  | 187575545 | The forecast radius tooltip on the map is misaligned
|  |  |  | 187569431 | In energy insights screen, Blueridge sites are displayed under other portfolios
May 13 - May 17 | 6 | Week 20 Week20_1 Prodv3.7.2 Week20_2(hotfix) Week20_3 Prodv3.7.3 | 4 | 187601633 | No hand symbol appears when hovering over add-on feature icon.
|  |  |  | 187600298 | The error message "Inverters not configured for the selected site" is not shown when a site with no configured inverters is selected.
|  |  |  | 187593060 | In the zone summary table, an error count is displayed for a tracker with 100% availability.
|  |  |  | 187624943 | At site level, only site summary card is seen. All other cards are missing.
May 20 - May 25 | 1 | Week 21 | 5 | #187632917 | Issue summary table is not loading.
|  |  |  | #187634535 | When date range of maintenance log is not within "last 7 days" range, the 'Adjusted for Maintenance Activities' icon can be removed from the tracker availability card.
|  |  |  | #187634702 | Settings icon missing after adding maintenance logs in Overview screen
|  |  |  | #187657661 | There was no increase in availability value observed after adding maintenance logs with operational trackers.
|  |  |  | #187657530 | 500 error when removing selected time in site maintenance screen.
|  |  |  | #187665652 | 500 internal server error in model viewer screen.
May 27 - May 31 | 4 | Week22 Week22_1 ProdV3.8 Week22_2 | 11 | #187684249 | In Issue summary table, the occurrence data is displayed for times outside the selected range
|  |  |  | #187695885 | UI issues in manage reports
|  |  |  | #187697171 | Alert should be shown while deleting a chart in My Dashboard which is used in report scheduling.
|  |  |  | #187697303 | unhandled rejection error while creating scheduled-report for miacomet site.
|  |  |  | #187698378 | Unable to delete the scheduled report if report title has special characters.
|  |  |  | #187698580 | Showing data for last 2 days even though in the report scheduling, value for last n days is given as 1.
|  |  |  | #187698667 | Received mail with content as No data available, report name was not mentioned.
|  |  |  | #187706021 | Discrepancy Between UI and BQ Values for Energy Production at Cabin Creek Site
|  |  |  | #187707193 | Last day data is not displayed in Scheduled Report if "Last n days" is set to more than 2 days
|  |  |  | #187707193 | First/Last day data is not displayed in Scheduled Report if "Last n days" is set to more than 1 day
|  |  |  | #187714870 | In Scheduled Historical Performance Chart Report, timestamp data not displayed in correct date order and time should start from 00:00.

## June 2024
No.of.Test builds | 19
No.of.Production builds | 4
Date | Build count | Builds released | Defect Count | Defect ID | Defect name
June 3 - June 7 | 5 | Week23 Week23_1 Week23_2 Week23_3 Prodv3.8.1 | 9 | #187747644 | On selecting the device graph icon in the tracker details column in the model viewer screen, it does not redirect to the overview screen.
|  |  |  | #187733614 | SUNOPS name is misspelled in the alert message.
|  |  |  | 187733555 | File name displays as [object Object] instead of Chart name in Scheduled My Dashboard report
|  |  |  | 187733739 | Historical performance report shows current day data in previous date
|  |  |  | 187754068 | The device ID is displayed as "ZC" when a custom chart report is initially scheduled with multiple metrics and then changed to a single metric.
|  |  |  | 187754276 | The report table column headers overlap with report details when scrolling up in Report table
|  |  |  | 187740219 | In sample download of historical performance report, remove ts column and display dates in time_key column in ascending order.
|  |  |  | 187739643 | When there is no data for flood level summary report , in the sample download empty excel with some special character is seen.
|  |  |  | 187754676 | Received error report mail when error /windspeed summary report is scheduled
June 10 - June 14 | 7 | Week24 Week24_1 Week24_2 Week24_3 Week24_4 Week24_5 Week 24_6 | 15 | #187764405 | Got request failed with status code 500 on logging the activity.
|  |  |  | #187770494 | 30 days old text over the activity should be removed once the activity is ended.
|  |  |  | #187764459 | Maintenance activity, that is yet to be started is not listed under "not started" heading.
|  |  |  | #187770571 | The maintenance logs entered previously are not appearing in the recent activities section on the site maintenance screen.
|  |  |  | 187762492 | Need validation to restrict metrics to the appropriate level for downloads in scheduled report
|  |  |  | 187764579 | For availability impact summary report got report with file name extension as .bin
|  |  |  | 187764300 | Getting negative value -50 for positional accuracy.
|  |  |  | 187770502 | Time stamp column is not seen for the scheduled download screen reports.
|  |  |  | 187770423 | Received historical performance report with 2 days data for n=1
|  |  |  | 187771139 | Received 25 hours data for n= 1 for the reports scheduled on download screen.
|  |  |  | 187794804 | For the 'last' and 'first' value aggregation types, data mismatches occur in the exported file for the same timestamp on every download.
|  |  |  | 187791436 | Received Sunops error report for some of the scheduled reports.
|  |  |  | 187791324 | Received value as -50 for availability in scheduled availability vs Error report
|  |  |  | 187790151 | For the scheduled overview screen reports, sheet name should be as in Sunops.
|  |  |  | #187787461 | After adding maintenance activity, there is no increase in availability value in historical performance chart.
June 17 - June 21 | 3 | Week 25 Prodv3.8.2 Week25_1 | 3 | 187814554 | When a new user logs into SUNOPS via email, they should be redirected to sunops.ftcsolar.com.
|  |  |  | 187821654 | In Live status, the filter icon should be removed from the column header when all checkboxes are selected
|  |  |  | #187835223 | Due to heavy processing server goes down
|  |  |  | 187821737 | No validation displayed for uploading a CSV file with incorrect tracker ID in Import custom metric
June 24 - June 28 | 8 | Prodv3.8.3 Week26 Week26_1 Week26_2 Week26_3 Week26_4 Week26_5 Prodv3.8.4 | 14 | #187851428 | For some of the scheduled custom chart reports, column header as 0 and 1.
|  |  |  | #187852598 | Need asterisk symbol for mandatory fields in report scheduling page.
|  |  |  | #187852715 | Active power summary chart should only be listed for sites where we have inverter data
|  |  |  | #187853308 | Recommendation is not shown for tracker outage followed by communication fault.
|  |  |  | #187859152 | Issue summary keeps on loading
|  |  |  | 187859201 | Critical alerts name are not displayed in zone outage recommendation at site
|  |  |  | 187859187 | In inclinometer recommendation, 2nd and 3rd points are not displayed
|  |  |  | #187860417 | Not able to select past date while ending ongoing activity.
|  |  |  | #187860283 | Issues in "Remind me" field
|  |  |  | #187860189 | After adding ongoing maintenance activity, availability value is calculated for present date
|  |  |  | #187859083 | Diffuse settings screen should be visible only at site level
|  |  |  | 187865857 | Recommendation is not shown for mechanical overload fault
|  |  |  | 187867583 | Issue name is not displayed and when clicked something went wrong error is seen
|  |  |  | 187866285 | Something went wrong error at device level

## July 2024
No.of.Test builds | 17
No.of.Production builds | 3
Date | Build count | Builds released | Defect Count | Defect ID | Defect name
July 01 - July 05 | 6 | Week27 Week27_1 Week27_2 Week27_3 Week27_4 Week27_v3.8.5 | 13 | 187882841 | Received mail twice for some of the scheduled reports.
|  |  |  | 187883419 | Expected Energy production and Power timeline not displayed for last 7 Days
|  |  |  | 187884836 | Incorrect metrics shown in the tracker outage recommendation
|  |  |  | 187884917 | If the issue happens due to bad weather, then it should be applicable for all the devices in that zone.
|  |  |  | 187891732 | In live status screen, column header overlaps with data in the view when scrolling up .
|  |  |  | 187892088 | Disclaimer message should be added in issue summary if the site/zone is not communicating more than 90 days.
|  |  |  | 187891612 | The "New" label is incorrectly displayed for the first log in the list instead of the actual newly added log
|  |  |  | 187903775 | Mismatch between issue summary and error summary.
|  |  |  | 187903903 | Site with outages are not listed in the "Site with no data"
|  |  |  | 187909950 | Showing wrong recommendation for tracker with no data at zone level /site level.
|  |  |  | 187910465 | Invalid date is displayed in the "Sent At" column when a new report is added or the frequency is edited for an existing report.
|  |  |  | 187892095 | The ascending order sort icon is displayed in the start time column but the data is not sorted.
|  |  |  | 187898401 | Mechanical overload occurred error should not be shown at device level.
July 08 - July 12 | 5 | Week28 Week28_1 Week28_2 Week28_3 Week28_v3.8.6 | 9 | 187917992 | RTC failure recommendation is displayed for both RTC failure and outage, instead of showing the RTC outage recommendation
|  |  |  | 187932629 | After logging an ongoing or not started activity, not able to see those logs even if "Do it now" option is selected or after refreshing the page
|  |  |  | 187934227 | The availability value is not increasing when an ongoing activity is added
|  |  |  | 187927059 | In Individual report : 'last' and 'first' value aggregation types, data mismatches occur in the exported file for the same timestamp on every download.
|  |  |  | 187940485 | The availability value is not reverting back when the ongoing activity is ended for past day
|  |  |  | 187939556 | Reminder date should be shown for a activity .
|  |  |  | 187939443 | Able to set reminder/end activity for the logs created by other users
|  |  |  | 187945602 | Not able to end activity/set reminder for the logs in table view
|  |  |  | 187945905 | It is taking more time to end an activity if it is reverted back for more days.
July 15 - July 19 | 3 | Week29 Week29_1 Week29_v3.8.7 | 7 | 187963765 | The new flag is not showing for the recently added release note if the 'Do it now' option is selected in the notification.
|  |  |  | 187963505 | In Download screen the metrics are not showing
|  |  |  | 187955479 | On the download screen, many test zones are showing for the CO29 site.
|  |  |  | 187954676 | Tracker ID is not shown in the search field in the bread crumb.
|  |  |  | 187954533 | Showing UTC time instead of site's local time at site level.
|  |  |  | 187977123 | Not getting notification when an ongoing activity is reverted for 30days old log
|  |  |  | 187977182 | On refreshing the page before job scheduler ends, the activity moves to complete without reverting availability value
July 22 - July 26 | 3 | Week30 Week30_1 Week30_2 | 8 | 188012759 | No data available is displayed when chapman file is uploaded
|  |  |  | 188012810 | For Hartsmill site, DID's of zone 7 is not getting imported.
|  |  |  | 188012474 | When there are 2 DID files for a site, after uploading 2 files it is showing only the DID's in the second file.
|  |  |  | 188017694 | For few sites, some of the DID's are not imported into sunops
|  |  |  | 188018501 | DID is imported twice when the read file button is clicked two times
|  |  |  | 188025831 | No data available is displayed when Starvation file is uploaded
|  |  |  | 188025823 | Zone ID is displayed incorrectly with Site ID prefix for first device in Chomogonday
|  |  |  | 188012158 | UI issues in Import DID
July 29 - July 31 | 3 | Week31 Week31_1 Week31_2 | 6 | 188027666 | The availability value is not increasing when an ongoing activity is added
|  |  |  | 188033472 | The page kept on loading when the job status is in progress
|  |  |  | 188027833 | Able to end same activity multiple times
|  |  |  | 188034164 | Throwing error while deleting invalid rows in UI.
|  |  |  | 188028011 | Throwing 400 error while importing DID file for alkali site
|  |  |  | 188042139 | Timestamp incorrectly displayed from selected time in download screen

## August 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Aug01 -Aug02 | 2 | Week31_3 Week31_v3.8.8 | 3 | 188048664 | Not able to do any activity in maintenance screen (add/end/set reminder).- Inconsistent | p3 - Low | Unstarted
|  |  |  | 188048538 | Issue with job status in site maintenance | p3 - Low | Unstarted
|  |  |  | 188048310 | The availability value is not reverting for the end date | p3 - Low | Accepted
Aug05 -Aug09 | 3 | Week32 Week32_1 Week32_2 | 9 | 188075732 | The offline tracker count is showing negative for some sites | p1-High | Accepted
|  |  |  | 188089413 | Sum of tracker count in offline card at site level is not matching with tracker count at portfolio level | p3 - Low | Accepted
|  |  |  | 188089790 | Issue with zone dropdown in the offline tracker detailed view | p3 - Low | Rejected
|  |  |  | 188063696 | The total RC count in offline card is greater than total RC count in error card | p2- Medium | Accepted
|  |  |  | 188090512 | The offline tracker count is shown in negative when sync is happening | p3 - Low | Accepted
|  |  |  | 188063740 | UI issues in offline tracker stat card. | p3 - Low | Accepted
|  |  |  | 188089803 | Some sites and zones are showing as online in offline trackers detailed view but it is a non reporting zone. |  | Accepted
|  |  |  | 188083405 | Incorrect occurrence value shown for Sites with no data in the detailed issue summary CSV | p3 - Low | Accepted
|  |  |  | 188083522 | Issue with No Site Data in the detailed issue summary CSV | p3 - Low | Accepted
Aug12 - Aug16 | 3 | Week33 Week33_1 Week33_v3.8.9 | 3 | 188099742 | Issue summary is not loading/refreshing or taking more time to load when selecting a custom date range of 1 month at portfolio level | p3 - Low | Unstarted
|  |  |  | 188100143 | Error in loading offline tracker stats after selecting VA113 site | p3 - Low | Accepted
|  |  |  | 188084918 | Issues in zone online/offline indication. | p2- Medium | Accepted
Aug19 - Aug23 | 4 | Week34 Week34_1 Week34_2 Week34_3 | 4 | 188134414 | Mismatch between device count in portfolio summary CSV and detailed CSV | p3 - Low | Accepted
|  |  |  | 188147146 | Offline zones are incorrectly shown as online | p3 - Low | Unstarted
|  |  |  | 188147418 | For some sites, incorrect offline zone count is shown | p3 - Low | Unstarted
|  |  |  | 188161886 | Issues with greater than 30 days are not shown in the error summary | p2- Medium | Unstarted
Aug26 - Aug30 | 4 | Week35 Wee35_1 Week35_2 Week35_3 | 9 | 188169283 | Issue with Avg and Max duration column sorting | p3 - Low | Started
|  |  |  | 188176461 | Mismatch in issue occurrence at site level | p2- Medium | Unstarted
|  |  |  | 188170710 | In Harts Mill site, issue name is blank for some rows. | p3 - Low | Unstarted
|  |  |  | 188170690 | Something went wrong error when All option is selected in portfolio dropdown. | p1-High | Accepted
|  |  |  | 188183312 | Something went wrong error while shifting to some other portfolio from All Portfolio. | p2- Medium | Accepted
|  |  |  | 188183726 | If All option is selected in portfolio dropdown, issue name is blank for last 2 rows in issue summary table. | p3 - Low | Unstarted
|  |  |  | 188196301 | Custom charts get deleted automatically | p1-High | Unstarted
|  |  |  | 188190769 | Not able to create/edit/delete a chart after deleting an existing chart | p3 - Low | Unstarted
|  |  |  | 188190833 | Need scroll option for My dashboard when multiple dashboards are created. | p3 - Low | Unstarted

## September 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Sept2 -Sept6 | 3 | Week36 Week36_1 Week36_2 | 4 | 188216561 | Disclaimer needs to be updated at site,zone and tracker level | p3-Low | Accepted
|  |  |  | 188231953 | Not able to download sample report for issue summary got something went wrong error | p2- Medium | Unstarted
|  |  |  | 188206093 | Over current fault is showing in the error summary but it is not showing up in issue summary | p3-Low | Unstarted
|  |  |  | 188271958 | Mechanical overload and communication fault is not showing in issue summary . | p2- Medium | Unstarted
Sept16 -Sept20 | 1 | Week38 | 7 | 188272231 | In live status, got type error when searching for site id at portfolio level | p3-Low | Unstarted
|  |  |  | 188289938 | Tracker communication metric should be shown in csv and pdf downloads of historical performance chart. | p2- Medium | Finished
|  |  |  | 188294841 | The tracker communication value is less than availability for some sites. | p1-High | Unstarted
|  |  |  | 188295002 | Issue with Tracker communication average at Invenergy portfolio summary | p2- Medium | Unstarted
|  |  |  | 188294918 | Error in loading stat cards after navigating from Lick creek site. | p3-Low | Unstarted
|  |  |  | 188296401 | Mismatch between tracker last updated time in summary table and tracker offline card table | p1-High | Unstarted
|  |  |  | 188302214 | "No data" should be shown for tracker communication metric when there is site outage. | p3-Low | Accepted
Sept23 - Sept27 | 2 | Week39 Week39_1 | 5 | 188324778 | Tracker communication is empty for offline sites/zones/tracker in the summary table. | p3-Low | Accepted
|  |  |  | 188330524 | For tracker communication metric it is showing as 0 instead of "No data". | p3-Low | Unstarted
|  |  |  | 188309989 | Accuracy is shown as "No data" instead of showing "Not calculated" when opening the site/zone/tracker in new tab | p3-Low | Unstarted
|  |  |  | 188330356 | The offline tracker count is showing in negative due to incorrect offline tracker count (Inconsistent) | p3-Low | Unstarted
|  |  |  | 188324887 | When exporting summary table, last sent column is not available in the exported file. | p3-Low | Unstarted
2024-09-30 | 1 | Week40__v3.10 | 1 | 188353977 | Tracker communication is showing as "No Data" even though there is data in Bigquery. | p3-Low | Unstarted

## October 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Oct1-Oct4 | 1 | Week40 | 1 | 188380255 | For sigurd site, mode summary chart is not back filled for 30th October. | p1-High | Accepted
Oct7-Oct11 | 1 | Week41 Week41_v3.11 | 7 | 188387433 | Data missing in tracker communication 30 mins table and zone_24Hrs table for July and August month. | p1-High | Accepted
|  |  |  | 188372558 | Tooltip for notification service and add on features overlaps on date time picker. | p1-High | Accepted
|  |  |  | 188400374 | Data missing in availability table | p3-Low | Unstarted
|  |  |  | 188401812 | In Portfolio detailed CSV, the tracker communication column is empty instead of showing "No data" | p3-Low | Accepted
|  |  |  | 188387438 | Tracker communication average should be calculated only for reporting devices | p2- Medium | Accepted
|  |  |  | 188387450 | Tracker communication is shown as No data instead of showing 0 in summary table | p2- Medium | Accepted
|  |  |  | 188419685 | Not able to create a new project or send notifications for existing project in Notification service | p0-Critical | Unstarted
Oct14-Oct18 | 1 | Week42 | 2 | 188441364 | The realtime issue is seen in Tracker Communication | p0-Critical | Unstarted
|  |  |  | 188441474 | For last 7 days, in historical performance it shows data for 8 days including current date | p0-Critical | Unstarted
Oct21-Oct25 | 0 | Week43- No build | 1 | 188446288 | Tracker communication shows as "No data" for Oct 17th | p0-Critical | Unstarted
Rearchitecture(New Sunops) Defects
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Oct 1 - Oct 04 | 1 | Week39 | 5 | 5086 | Current Angle Summary value is incorrectly shown as 0 | p3 | Fixed
|  |  |  | 5087 | Dropdown(site/zone/device) is not refreshing on changing the portfolio/site/zone. | p1 | Resolved and blocker 5203
|  |  |  | 5088 | Data is shifted backward by 1 time interval | p1 | Fixed
|  |  |  | 5090 | Error and Mode filtering not applied at Zone and Site levels for trackers with multiple Errors and Modes | p1 | Resolved and blocker 5195, 5205
|  |  |  | 5116 | Wind Speed chart is not loading for APEX site. | p2 | Fixed
Oct 07 - Oct 11 | 1 | Week40 | 5 | 5117 | Data mismatch between New Sunops and Production Sunops for ZC and Current Angle Charts | p1
|  |  |  | 5118 | For some sites extra row is displayed in Exported Wind Summary chart file | p3
|  |  |  | 5119 | Error and Mode Summary Charts are not loading at Portfolio level | p1 | Fixed
|  |  |  | 5120 | Mechanical overload occurred error should not be shown at device level | P2 (Known prod issue)
|  |  |  | 5122 | Charts are not loading when more than 2 months is selected in date time picker | p2
|  |  |  | 5123 | Data missing and mismatch between Pinot and Big query (Tested for 3 months) | p1
Oct 14 - Oct 18 | 1 | Week42 | 2 | 5123 | Data missing and mismatch between Pinot and Big query (Tested for 1 year) | p1
|  |  |  | 5137 | Zones are not listed in the "Zones" dropdown | p1 | Closed
|  |  |  | 5136 | The loading cursor is not visible when the charts take time to load. | p2
Oct 21 - Oct 25 | 1 | Week43 | 11 | 5144 | Alarm counts for all Zones incorrectly displayed as 0 in Site summary table | p2
|  |  |  | 5143 | At the site level, the availability average is incorrectly calculated as a normal average instead of a weighted average | p1
|  |  |  | 5145 | Availability Impact Summary Chart data not refreshing when changing Sites/Zones/Devices and sometimes not loading | p1
|  |  |  | 5141 | Availability mismatch due to the availability shown as 0 instead of showing null during site outage | p1
|  |  |  | 5155 | Availability vs Errors Chart data is not matching with Summary table data | p1
|  |  |  | 5152 | Error count mismatch between QA and SunOps Production | p2
|  |  |  | 5153 | Incorrect values shown in Availability Impact Summary Chart | p1
|  |  |  | 5150 | Last sent column in portfolio summary table is not updated it is showing last updated as > 30 days(checked for blueridge portfolio) | p1
|  |  |  | 5146 | Mismatch in total Sites/Zones/Devices in Summary Card | p1
|  |  |  | 5148 | The portfolio summary card does not load when a period of more than 4 months is selected(from 01-06-2024) | p1
|  |  |  | 5151 | When a time period of more than 3 months is selected, the 'View Zones' button does not appear on the site summary card | p1
Oct28 - Nov 1 | 1 | Week44 | 10 | 5156 | Portfolio summary table is not refreshing while changing the portfolio | p1
|  |  |  | 5158 | Tracker Availability Card is not loading at Portfolio level | p2
|  |  |  | 5195 | At the device level, all errors and modes should be displayed without any prioritization | p2
|  |  |  | 5201 | Got something went wrong error when navigating to Site /Zone (Inconsistent) | p1
|  |  |  | 5203 | Portfolio's are not listed in the portfolio dropdown | p1
|  |  |  | 5204 | At the portfolio level, the device count in Mode and Error Summary is lower in New Sunops than in Production. | p1
|  |  |  | 5205 | Error should be prioritized at device , zone , site and portfolio level | p1
|  |  |  | 5206 | Data is missing in the Error and Mode Summary chart when the value is zero | p2
|  |  |  | 5207 | At Portfolio and Site levels, Mode and Error Summary displays chart from selected time instead of next interval | p2
|  |  |  | 5208 | Custom charts are not populating | p1

## November 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Nov4-Nov8 | 0 | Week45 | 3 | 188512117 | Model viewer for heighliner and Falcon site is not loading. | p0
|  |  |  | 188525595 | In demo server, Got something went wrong error when navigating to Hail settings | p2
|  |  |  | 188525602 | Summary card, Tracker availability card, Tracker offline card, Historical performance chart and Issue summary are not loading in demo server | p1
Nov11-Nov15 | 0 | Week46 | 5 | 188555000 | Tracker communication table is not backfilled, displays 0 from 11:30pm to 12:00am | p1
|  |  |  | 188557343 | Custom dashboard with Total RC and Recent value charts causes page unresponsiveness and Server down | p0
|  |  |  | 188557374 | In Custom Charts, need validation for total RC value type | p2
|  |  |  | 188568288 | When creating a new chart, "Share within the organization" checkbox should be set to unchecked by default | p3
|  |  |  | 188572937 | Able to access Hail and Diffuse features by directly navigating to the URL, even if these settings are disabled for the user profile | p1
2024-11-28 | 0 | Week48 | 1 | 188627476 | Data is not backfilling when arriving late | p1

## December 2024
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Status
Dec2-Dec06 | 1 | Week49 | 1 | 188637191 | The device count for a zone differs when viewed at the site level compared to the zone level
Dec9-Dec13 | 2 | Week50 Week50_v3.12 | 7 | 188676905 | Higher error count displayed when selecting date ranges greater than 15 days | P1
|  |  |  | 188680975 | UI issues in BOM feature | P2
|  |  |  | 188680979 | BOM metric is not shown at the direct downloads metric dropdown | P2
|  |  |  | 188681761 | Not able to redirect to Notification service | P1
|  |  |  | 188676892 | Invalid error count as array length in error count query wrongly returns value as 64 in some scenarios | P1
|  |  |  | 188681673 | Showing wrong value in the exported file if total rc's is selected as value type while creating custom charts | P3
|  |  |  | 188681694 | When hovering over the custom chart, the pop-up does not display all the faults when the zoom level is set to 100% | P3