## Nov24
Weekly Status Report
| Week -47 | 18-11-2024 to 22-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8hrs x 5days) = 40 | In Sundat, tested basic sanity for the new server. Executed sanity automation suite in new sundat server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 6 Filed defects count: 12 |  | P1- 5308, 5307, 5303, 5310,5311,5312,5313,5320,5319,5314,5318 P2- 5315
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 3days) = 24 | In Sundat, tested basic sanity for the new server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 4 Filed defects count: 8 |  | P1- 5310, 5312, 5323, 5324 P2- 5299, 5300, 5302, 5325
| Week -48 | 25-11-2024 to 29-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested important features in SunDAT after deploying in azure server 2.In NewSunops, tested live status and downloads features. 3.Validated the issues fixes delivered by Harman team. .No.of defects validated:8 No of defects filed :9
P1-5314 p2-5330,5331,5333, 5344,5345,5346,5347, 5349
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | Features tested, Filed defects count, Number od defects validated,Number of test cases written/updated
Defect ID of Defects with priority(P0,P1…)

## Dec24
| Week -49 | 02-12-2024 to 06-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validated the issue fixes . No.of defects validated-8 No of defects filed - 2 2.Analysed the extra timestamp columns added for different time intervals in Readings_2 table 3.Tested SunDAT after changing the dbabi and jsapi. |  | P2-5362,188637191,5367
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.In New Sunops, Validated the issue fixes . No.of defects validated- 8 No of defects filed - 3 2. Tested the Readings_2 table in Pinot and analyzed the additional timestamp columns added for different time intervals 3. Updated test cases for Custom charts and Site maintenance 4.Tested SunDAT after changing the dbabi and jsapi. | Custom charts- 14 Site maintenance- 44 | P2- 5363, 5366, 5367
| Week -50 | 08-12-2024 to 13-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops
P1-5374,188676892,5402,5404 P2-5401,5388 P3-188681673,188681694
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 11 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops |  | P1- 5377, 5389, 5403, 188676905, 188681761 P2- 5375, 5405, 188680975, 188680979 P3- 5390, 5408
| Week -51 | 16-12-2024 to 20-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure.
P1-5409,5410,5411,188703177 188703244 P2-5426,5427,5428,5412
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 6 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure. |  | P1- 5410, 5429, 5389, 5431 P2- 5414, 5430

## Jan25
| Week -02 | 06-01-2025 to 10-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Sundat production server after DNS migration 2. Validated DID UI bug fixes in Test and Production server 3. In New Sunops, tested Error and Mode summary charts 4. In New Pinot server, Validated data in Readings table 5. Issues files: 5 |  | P1- 5448, 5449, 5456, 5466, 5452
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Sundat production server after DNS migration 2. Validated DID UI bug fixes in Test and Production server 3. In New Sunops, tested Error and Mode summary charts 4. In New Pinot server, Validated data in Readings table 5. Issues files: 5 |  | P1- 5450, 5467 P2- 5438, 5451, 5457
| Week -03 | 13-01-2025 to 17-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 36 | 1. In New Pinot server, Validated data in Readings table 2. Tested Availability, Positional Accuracy, Historical performance, Error Summary, Mode Summary, ZC charts, Live Cards, Live status and Availalability24Hours table 3. Validated and closed 6 bugs 4. Issues files: 14 |  | P1 - 5479, 5481, 5490, 5492, 5494, 5500, 5501, 5504, 5506, 5508 P2 - #188782680, #188782709, 5499, 5505
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 4days) = 36 | 1. In New Pinot server, Validated data in Readings table 2. Tested Availability, Positional Accuracy, Historical performance, Error Summary, Mode Summary, ZC charts, Live Cards, Live status and Custom charts 3. Validated and closed 6 bugs 4. Issues files: 17 |  | P1 - 5474, 5480, 5486, 5488, 5493, 5498, 5502, 5503, 5509, 5513, 5514, 188783069 P2 - 5475, 5482, 5483, 5507, 5510
| Week -04 | 20-01-2025 to 24-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. In New Pinot server, Validated the availability table 2. Tested Positional accuracy, Chart performance , Tracker with error and Zones communicating card 3. Issues files: 2 |  | P1- 5528 P2- 5533
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. In New Pinot server, Validated the availability table 2. Tested Positional accuracy, Chart performance , Tracker with error and Zones communicating card 3. Issues files: 2 |  | P1- 5531 P2- 5530
| Week -05 | 27-01-2025 to 31-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. Checked the currently reporting and non reporting sites and uploaded DID for reporting sites 2. In New Sunops, tested Issue summary and validated 10 bug fixes. Filed 8 issues. 3. In Sunops test server, Live at portfolio level and validated 2 bug fixes 4.Tested SunDAT in both QA and production server after migration |  | P1-5547,5555,5562,5541,5540 #188846492 #188840363 P3-#188846486
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. Checked the currently reporting and non reporting sites and uploaded DID for reporting sites 2. In New Sunops, tested Issue summary and validated 10 bug fixes. Filed 8 issues. 3. In Sunops test server, Live at portfolio level and validated 2 bug fixes |  | P1- 5536, 5541, 5546, 5544, 5545, 5561, 5563, 5568

## Feb25
| Week -06 | 03-02-2025 to 07-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Sunops test and production server - Tested the Live status at the Portfolio level and validated the 3 bug fixes. 2. In New Sunops, tested the issue summary, recommendation engine, downloads and performance of downloads 3. Filed 8 issues |  | P1-5581,5577,5576 P3-5548 P2-188862264,188861472 188852254,5571
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Sunops test and production server - Tested the Live status at the Portfolio level and validated the 3 bug fixes. 2. In New Sunops, tested the issue summary, recommendation engine, downloads and performance of downloads 3. Filed 7 issues |  | P1- 5575, 188853046 P2- 5579, 5589, 188852087, 188865643, 188857794
| Week -07 | 10-02-2025 to 14-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. In New Sunops, tested the recommendation engine, and performance of custom charts 2. In current Sunops, updated test cases for livestatus report at portfolio level. 3. Tested the sundat after updating aws keys for tg-api and all other api related to upload and download in production server. 4. Tested sunops demo server 4. Filed 3 issues | updated test cases for livestatus report at portfolio level. | P3-5609 P2-188893858,188893803
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In New Sunops, tested the recommendation engine, and performance of custom charts 2. In New Sumops, updated test cases for Historical Performance, Issue summary and Recommendation engine. 2. Tested the sundat after updating s3 aws keys for sundat db api in QA server. 3. Tested sunops demo server 4. Filed 4 issues | Historical performance- 9 Issue summary- 35 Recommendation engine- 31 | P2- 5606, 5607, 188893790 P3- 188893856