## Nov24
Weekly Status Report
| Week -47 | 18-11-2024 to 22-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8hrs x 5days) = 40 | In Sundat, tested basic sanity for the new server. Executed sanity automation suite in new sundat server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 6 Filed defects count: 12 |  | P1- 5308, 5307, 5303, 5310,5311,5312,5313,5320,5319,5314,5318 P2- 5315
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 3days) = 24 | In Sundat, tested basic sanity for the new server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 4 Filed defects count: 8 |  | P1- 5310, 5312, 5323, 5324 P2- 5299, 5300, 5302, 5325
| Week -48 | 25-11-2024 to 29-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested important features in SunDAT after deploying in azure server 2.In NewSunops, tested live status and downloads features. 3.Validated the issues fixes delivered by Harman team. .No.of defects validated:8 No of defects filed :9
P1-5314 p2-5330,5331,5333, 5344,5345,5346,5347, 5349
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | Features tested, Filed defects count, Number od defects validated,Number of test cases written/updated
Defect ID of Defects with priority(P0,P1…)

## Dec24
| Week -49 | 02-12-2024 to 06-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validated the issue fixes . No.of defects validated-8 No of defects filed - 2 2.Analysed the extra timestamp columns added for different time intervals in Readings_2 table 3.Tested SunDAT after changing the dbabi and jsapi. |  | P2-5362,188637191,5367
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.In New Sunops, Validated the issue fixes . No.of defects validated- 8 No of defects filed - 3 2. Tested the Readings_2 table in Pinot and analyzed the additional timestamp columns added for different time intervals 3. Updated test cases for Custom charts and Site maintenance 4.Tested SunDAT after changing the dbabi and jsapi. | Custom charts- 14 Site maintenance- 44 | P2- 5363, 5366, 5367
| Week -50 | 08-12-2024 to 13-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops
P1-5374,188676892,5402,5404 P2-5401,5388 P3-188681673,188681694
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 11 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops |  | P1- 5377, 5389, 5403, 188676905, 188681761 P2- 5375, 5405, 188680975, 188680979 P3- 5390, 5408
| Week -51 | 16-12-2024 to 20-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure.
P1-5409,5410,5411,188703177 188703244 P2-5426,5427,5428,5412
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 6 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure. |  | P1- 5410, 5429, 5389, 5431 P2- 5414, 5430
| Week -52 | 23-12-2024 to 27-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. Tested the device count mismatch between meta.devices and the uploaded DID for 71 sites (Brindha- 30 sites , RP- 30 sites). 2. Identified the devices present in meta.devices but not in the uploaded meta.commissioning_site_data , added comments and shared our observation with Jaya. 3. In DID, for missing devices in DID found the reporting and non reporting devices in each site and updated in the observation sheet.
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 4days) = 32 | 1. Tested the device count mismatch between meta.devices and the uploaded DID for 71 sites (Brindha- 30 sites , RP- 30 sites). 2. Identified the devices present in meta.devices but not in the uploaded meta.commissioning_site_data , added comments and shared our observation with Jaya. 3. In DID, for missing devices in DID found the reporting and non reporting devices in each site and updated in the observation sheet.

## Jan25
| Week -01 | 30-12-2024 to 03-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. Received a test build from Yash for DID 400 error fix , validated that and imported DIDs for 6 sites. 2. In New Sunops, tested error and mode charts performance in production at Portfolio and Site level. 3. Rearch server is now pointing to readings_3 table and tested Wind Direction, Wind Speed, Flood level, Snow fall and Current angle charts |  | P1- 5448,
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. Received a test build from Yash for DID 400 error fix , validated that and imported DIDs for 6 sites. 2. In New Sunops, tested error and mode charts performance in production at Portfolio and Site level. 3. Rearch server is now pointing to readings_3 table and tested Wind Direction, Wind Speed, Flood level, Snow fall and Current angle charts |  | P2- 5438
| Week -02 | 06-01-2025 to 10-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Sundat production server after DNS migration 2. Validated DID UI bug fixes in Test and Production server 3. In New Sunops, tested Error and Mode summary charts 4. In New Pinot server, Validated data in Readings table 5. Issues files: 5 |  | P1- 5449, 5456, 5466, 5452
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Sundat production server after DNS migration 2. Validated DID UI bug fixes in Test and Production server 3. In New Sunops, tested Error and Mode summary charts 4. In New Pinot server, Validated data in Readings table 5. Issues files: 5 |  | P1- 5450, 5467 P2- 5451, 5457
| Week -03 | 13-01-2025 to 17-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. In New Pinot server, Validated data in Readings table 2. Tested Availability, Positional Accuracy, Historical performance, Error Summary, Mode Summary, ZC charts, Live Cards, Live status and Availalability24Hours table 3. Validated and closed 6 bugs 4. Issues files: 14 |  | P1 - 5479, 5481, 5490, 5492, 5494, 5500, 5501, 5504, 5506, 5508 P2 - #188782680, #188782709, 5499, 5505
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 4days) = 32 | 1. In New Pinot server, Validated data in Readings table 2. Tested Availability, Positional Accuracy, Historical performance, Error Summary, Mode Summary, ZC charts, Live Cards, Live status and Custom charts 3. Validated and closed 6 bugs 4. Issues files: 17 |  | P1 - 5474, 5480, 5486, 5488, 5493, 5498, 5502, 5503, 5509, 5513, 5514, 188783069 P2 - 5475, 5482, 5483, 5507, 5510
| Week -04 | 20-01-2025 to 24-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. In New Pinot server, Validated the availability table 2. Tested Positional accuracy, Chart performance , Tracker with error and Zones communicating card 3. Issues files: 2 |  | P1- 5528 P2- 5533
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. In New Pinot server, Validated the availability table 2. Tested Positional accuracy, Chart performance , Tracker with error and Zones communicating card 3. Issues files: 2 |  | P1- 5531 P2- 5530
| Week -05 | 27-01-2025 to 31-01-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. Checked the currently reporting and non reporting sites and uploaded DID for reporting sites 2. In New Sunops, tested Issue summary and validated 10 bug fixes. Filed 8 issues. 3. In Sunops test server, Live at portfolio level and validated 2 bug fixes 4.Tested SunDAT in both QA and production server after migration |  | P1-5547,5555,5562,5541,5540 #188846492 #188840363 P3-#188846486
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrs x 5days) = 40 | 1. Checked the currently reporting and non reporting sites and uploaded DID for reporting sites 2. In New Sunops, tested Issue summary and validated 10 bug fixes. Filed 8 issues. 3. In Sunops test server, Live at portfolio level and validated 2 bug fixes |  | P1- 5536, 5541, 5546, 5544, 5545, 5561, 5563, 5568

## Feb25
| Week -06 | 03-02-2025 to 07-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Sunops test and production server - Tested the Live status at the Portfolio level and validated the 3 bug fixes. 2. In New Sunops, tested the issue summary, recommendation engine, downloads and performance of downloads 3. Filed 8 issues |  | P1-5581,5577,5576 P3-5548 P2-188862264,188861472 188852254,5571
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Sunops test and production server - Tested the Live status at the Portfolio level and validated the 3 bug fixes. 2. In New Sunops, tested the issue summary, recommendation engine, downloads and performance of downloads 3. Filed 7 issues |  | P1- 5575, 188853046 P2- 5579, 5589, 188852087, 188865643, 188857794
| Week -07 | 10-02-2025 to 14-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. In New Sunops, tested the recommendation engine, and performance of custom charts 2. In current Sunops, updated test cases for livestatus report at portfolio level. 3. Tested the sundat after updating aws keys for tg-api and all other api related to upload and download in production server. 4. Tested sunops demo server 4. Filed 3 issues | updated test cases for livestatus report at portfolio level. | P3-5609 P2-188893858,188893803
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In New Sunops, tested the recommendation engine, and performance of custom charts 2. In New Sumops, updated test cases for Historical Performance, Issue summary and Recommendation engine. 2. Tested the sundat after updating s3 aws keys for sundat db api in QA server. 3. Tested sunops demo server 4. Filed 4 issues | Historical performance- 9 Issue summary- 35 Recommendation engine- 31 | P2- 5606, 5607, 188893790 P3- 188893856
| Week -08 | 17-02-2025 to 21-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 0days) = 0 | Leave
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Sunops demo server 2. Updated test cases for Issue summary, Tracler communication calculation and historical performance in New sunops 3. Prepared a query document 4. In Sundat, tested project opening , creation and specsheets after resizing DBAPI prod and fileserver prod APIs 5. Filed 2 issues in Sunops demo server | Tracker communication- 15 Historical performance- 9 | P1- 188912398, 188912360
| Week -09 | 24-02-2025 to 28-02-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested performance of issue summary in rearch for last 7 days and 15 days interval. 2.uploaded those asbuilt files for 6 projects. Mani (site engineer) shared list of zones in Samson site which were not showing up in live status screen. We analysed the zones list and shared our observations to Mani team. 3.Received production build in Sunops .Tested the recent fixes in production server. 4.Tested the historical performance bug fixes in production sunops.
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 4days) = 32 | 1. Tested performace in Rearch 2. Tested issue summary in Demo server 3. In Sundat production, created a asbuild project for sites with Model viewer to push those models to Sunops and compared the terrain EA values 4. In Samson site, 1250 devices have no data in live status but shows last updated time. Checked those devices in BQ 5. Received a bug fix and tested the historical performance issue fix in Test server 6. Received a bug fix and tested last 7 days availability average in summary card and last 7 days card in Test server

## Mar25
| Week -10 | 03-03-2025 to 07-03-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In New Sunops, checked the API performance 2. Tested Custom charts with multiple time interval in the test and Production server 3. In Sundat, uploaded asbuild files for 6 projects and compared the terrain EA values between the test db and production 4. In Sunops, pushed Sundat model into Sunops model viewer and compared the value between test db and production 5. Filed 3 issues |  | P2-188949733 P3- 188962923, 188962798
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In New Sunops, checked the API performance 2. Testes Custom charts with multiple time interval in test and Production server 3. In Sundat, created asbuild project and compared the terrain EA values between test db and production 4. In Sunops, uploaded model viewer and compared the value between test db and production 5. Filed 3 issues |  | P3- 188962888, 188962908, 188952988
| Week -11 | 10-03-2025 to 14-03-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1..Uploaded Asbuilt files for below projects in sundat.ftcsolar.com VA17,VA28 and sweetspring. 2.Tested the performance of newsunops at site and portfolio level and share that report to Jaya. 3.Did one round of sanity in sundat production as Jaya asked to do Sanity after shutting down of few machines connected to SunDAT production server. 4.Worked on python script for pivotal migration.. |  | P3-#188962798 P2-#188962798,#188962923
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Compared the model viewer tracker mapping details in Sunops with Sundat test DB API and DWG file and tested Pinoneer GA 2. In New Sunops, tested user analytics, Hail settings 3. Tested Pinooer GA validation messages 4. Prepared Python script for story migration from Pivotal tracker to Azure (Field mapping for Title, Description, Story type, lables, Custom labels, Multiple labels, Owner mapping, Priority, Story status) |  | P1- 5693
| Week -12 | 17-03-2025 to 21-03-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Did data validation testing for readings table. 2.shared the history of the MO14 site in the devices table with Jaya. 3.completed the comments migration from Pivotal to Azure 4. executed the migration script by reading story ids from excel. 5..In the SunDAT test project , successfully migrated 320 stories to Azure . 6.Tested availability and tracker communication stat card, historical performance , availability , error and mode summary charts in MO14 site after removing the Zone: Default_ID
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 4days) = 32 Leave on 21-03-2025 | 1. Validated pinot readings table data from Sept 2024 to March 2025. 2. Prepared Python field mapping script for story migration from Pivotal tracker to Azure (Field mapping for Sub task in both bug and feature, Feature , Comments, Attachment, Sory points, Created by in the Feature story type 3. Prepared code for multiple story migration and read story id from excel sheet 4. Trail migration of 300 stories from Sunops to Sundat test project in Azure
| Week -13 | 24-03-2025 to 28-03-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Jaya asked to create report in such a way it should show the file attachment count in azure and pivotal against each story ID. Updated the migration script 2. Migrated 1500 stories from Sunops in Pivotal to Sundat test project in Azure 3. Migrated 3000 stories from Sundat in Pivotal to Sundat test project in Azurre 4. Compared the zone names between commisioning and devices table for all sites and shared the zone name pattern in each site to Jaya. 5.Validated the datas in the new device table created by Yash
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Updated the Pivotal story migration script to show the attachment summary report to show in console and data also saved in an excel file 2. Migrated 1500 stories from Sunops in Pivotal to Sundat test project in Azure 3. Migrated 3000 stories from Sundat in Pivotal to Sundat test project in Azurre 4. Compared the zone names in the devices and commisioning table for devices cleanup. Added a zone mapping to change the zone name in devices cleanup table 5. Tested the zone id names in the new_mapping table

## April25
| Week -14 | 31-03-2025 to 04-04-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested the zone mapping in meta.devices_cleanup_table( created by Jaya) for 77 sites and shared our observations with Jaya. 2.Identified the Duplicate device_id in commissioning table and shared those id's with Jaya. 3.Analysed the root cause for the device count mismatch in zone_cleanup table . 4.Migrated 3000 Sundat stories from Pivotal to Sundat project in Azure
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested the zone id names mapping between meta.devices and meta.commissioning tables in the devices_cleanup_tables 2. Added zone mapping doe 20 sites 3. Checked the duplicated devices in DID 4. Migrated 3000 Sundat stories from Pivotal to Sundat project in Azure
| Week -15 | 08-04-2025 to 11-04-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Tested the zone name clean up for 23 sites 2.Found DID files for the 11 sites and uploaded the same 3.Completed the pivotal migration for SunDAT project.(3000 stories)
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Tested zone name mapping for the sites in devices cleanup table 2. Uploaded DID file for 12 sites 3. Migrated 3000 Sundat stories from Pivotal to Sundat project in Azure
| Week -16 | 14-04-2025 to 18-04-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.completed the Pivotal Tracker migration for both SunOps and SunDAT projects. 2.Zone name cleanup was tested across 32 sites. 3.Tested the zone traverse for all site list given by Jaya. 4.Validated the Export option in user analytics screen. |  | P2-1576
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Migrated 1500 Sunops stories from Pivotal to Sunops project in Azure 2. Added zone mapping regular exp for 12 sites and tested zone cleanup for 34 sites. Tested the 34 sites in cleanup_duplicate table 3. Checked the devices with Zone traversal in active devices table for sites 4. Validated 15 days of data in Pinot Readings table 5. Tested export feature in User analytics in Sunops test and prod 6. Filed 2 issues |  | P1- 6318 P2- 1576
| Week -17 | 21-04-2025 to 25-04-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Completed data validation for 15 days data in availability and positional accuracy table in new sunops 2.Completed the Data validation for 3 months of data in pinot readings table. 3.Tested the zone name clean up for 30 sites. 4.Tested the site traversal of devices for the second batch of 30 sites. |  | P1-6337,6334 P2-1578
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Tested the zone cleanup table for 93 sites after adding additional devices fromDID file to devices cleanup table 2. Tested 30 sites in dcp_dup table after merging the sites name for some sites 3. Checked the zone traversal pattern for zones where zone movement is across different zones 4. Validated 15 days of data in Pinot readings, availability 30mins, availability 24hrs, uptimebase and issue summary tables 5. Validated 3 months of data in Pinot readings, availability 30mins, availability 24hrs, uptimebase and issue summary tables 6. Filed 3 issues |  | P1 - 6341 P2- 6336, 6338
| Week -18 | 28-04-2025 to 02-05-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 4days) = 32 | 1.Validated the 20 issue fixes delivered by Harman team. 2.Did data validation in pinot readings table for the month of october 2024, november 2024and march 2025 3.Tested the site traversal for remaining 15 sites and had call with cotrol system team and share the observation on site traversal. 4.Tested the voyager and pioneer GA in remote machine. |  | P1-6386,6346,6357
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 4days) = 32 | 1. In New Sunops, Validated the 19 bug fixes, closed 4 issues, rejected 8 issues 2. Validated 9 months of data in Pinot readings table 3. Checked Site traversal in the active devices table 4. Retested the 20 bugs which are not depended on the pre-populated tables and closed 5. Filed 4 issues |  | P1- 6386, 6389, 6356, 6356

## May25
| Week -19 | 05-05-2025 to 09-05-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.In SunDAT, Tested the newsalesforce change and received the production build for the same. 2.In newsunops validated the whole one year of data in reading table. 3.Tested the SunDAT production server after moving production server into VPN. 4.Validated the issue 20 issue fixes delivered by Harman team |  | P2-13551,13552,13554,13553,1581,6392,6395,6399
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Validated data in Pinot readings table from May 2024 to April 2025. And validated metric summary table from Oct 2024 to March 2025 2. Validated the live ingestion in Pinot readings table 3. Tested Error and Mode summary in New Sunops 4. Checked the API performance in New Sunops 5. Done JMeter setup for load testing 6. Validated 17 issues fixes in New Sunops Filed 6 issues |  | P1- 6393, 6396, 6397, 6398, 6400 P2- 1580
| Week -20 | 12-05-2025 to 16-05-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1..Completed the data validation for issue summary pre populated tables. 2.Validated the metric summary table from 01-03-2025 to 12-04-2025 and no data missing is seen. 3.Validated 12 bug fixes delivered by Harman team |  | P2-1583 ,6417,6434 P1-6404,6416
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Validated issue summary prepopulated, Availability24hours and Uptime24hours tables 2. In Sunops test server, tested error code metric in downloads for multiple errors occuring in single device 3. Tested total RC value type in Custom charts 4. Validated 12 issue fixes in the New Sunops 5. Filed 6 issues |  | P1- 6401, 6403, 6405, 6413, 6415, 6431
| Week -21 | 19-05-2025 to 23-05-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validated the metric summary table from October 2024 to May 2025. except for Feb 2025 since harman team is reloading for this month. 2.Tested the performance of error , mode and ZC charts at portfolio and site level. 3.Retested the issues in zones communicating card in new sunops . 4.Tested the availability in new sunops after populating the 6 months of data. 5.Retested and closed 7 bugs in Azure board |  | P1-6454 P2-1584,6455 ,1585 P3-6447
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 4days) = 32 Leave on 21-05-2025 | 1. Validated the metric summary table from October 2024 to May 2025 and tested error and mode summary 2. Tested the performance of error, mode, and ZC charts at Portfolio and Site level 3. Tested device count realed features (Trackr with Errors and Device count in Summary table) 4. Tested the availability and validated availability pre-populated tables from Jan 2025 to May 2025 5. In JMeter, added all 19 Overview APIs to the Test plan and tested for 1 user 6. Retested and closed 9 issues in Azure Filed 3 issues |  | P2- 6445, 6448, 6462
| Week -22 | 26-05-2025 to 30-05-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 4days) = 32 leave on 28-05-2025 | 1.tested positional accuracy and availability. 2.Tested the performance of overview , error and mode charts at all levels 3.Checked the way to watch CPU utilization of the Pinot server when a request hits the server. Requested Jaya for access to connect AKS cluster 4.Validated live Data ingested into pinot readings table.. |  | P1-6464 ,6465 ,6481 P2-6467
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested Historicaal performance chart , Positional accuracy and Availability 2. Tested APIs performance at portfolio and site level. 3. Validated the Availability and Uptimebase pre-populated tables after the schedulers started running live 4. Validated live ingetion in readings table 5. In Load testong, tested with 1 to 5 users, 10, 15, 20 , 25 and 30 users ar Site level 6. Checked the kubectl commands to check CPU utlization of Pinot server Filed 2 issues |  | P1- 6462, 6466

## Jun25
| Week -23 | 02-06-2025 to 06-06-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested the historical performance charts. 2. Prepared the document to install require softwares in remote machine so as to execute automation script for SunDAT in remote machine.shared the document to Jaya to raise a ticket to IT team. 3.Received test build from Yash for sales force change in voyager GA and tested the same in SunDAT test server. |  | P1-6485 P2-13555,13557 P3-13556
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 4days) = 32 Leave on: 06-06-2025 | 1. Validated live ingestion data in Pinot readings table and tested the API performance at Portfolio and Site level 2. Tested the availability and historical performance chart 3. Prepared the automation software installation document to raise a ticket to IT team to get it installed in Remote machine 4. Tested the Voyager GA and Pioneer GA in Sundat test server after the Salesforce changes 5. Updates test cases for Availabilty, Positional accuracy and Tracker communicaton calculation logic in backend table | Availabilty- 14 Positional accuracy- 16 Tracker communicaton- 15 | P1- 6486
| Week -24 | 09-06-2025 to 13-06-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. installed automation software in (test server) 2.Validated the one year data in pinot reading table and shared our observation to the team. 3.Validated the 10 issue fixes delivered by Vinoth and tested the related features. 4.As per Jaya's request, checked the sites that were sending one-year-old data to the Readings table (as observed yesterday) and shared the findings with her 5. Tested Zones communication card, Last sent column and Availability impact summary chart |  | P1- 6531 ,6543
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Remote machine , installed the required automation software and executed the script in edge browser 2. Validated the performance in New sunops 3. Validated data in Pinot readings table from Jan 2025 to March 2025 4 Validated Availability and Uptimebase pre-populated tables 5. Validated the 10 issue fixes in New Sunops. 6. Tested Zones communication card, Last sent column and Availability impact summary chart Filed 4 issues |  | P1- 6532, 6533, 6334, 6544
| Week -25 | 16-06-2025 to 20-06-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validated the offline Zone feature in new sunops and rejected the bug. 2.Tested the site and Zone outage in report scheduling 3.Validated offline zone count fix given by Vinoth 4.Tested the performance in newsunops after Vinoth gave fix for errorpage which is shown when APIs were failing. 5. Validated the MetricSummary_60mins table |  | 1594-P2 1593-P3 6587-P1
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. In Sunops test and producation server, tested the Site and Zone outage reports at Scheduled report. Tested sanity in Production server 2. In New Sunops, tested the last sent column, avilability impact summary and availability average in Summary card 3. Tested the May , June month performance in New sunops to validate the auth error show when APIs failing. 4. Tested zones communicating card in New sunops after the bug fix 5. Validated Error Code, Current mode and ZC metrix data in MetricSummary_60mins table from Oct 2024 to Dec 2024 Filed 3 issues |  | P1- 6560, 6584, 6589
| Week -26 | 23-06-2025 to 27-06-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1..Validated and closed Zones communicating card issue fixes. 2.Performed load testing for 15 users(as Jaya asked to test for 15 users) last seven days at the portfolio level using JMeter and monitored CPU utilization. Observed that CPU usage increases when requests hit the server 3.Installed the required software for running the automation script on the SunDAT production remote machine. 4.Validated 7 P0 issue fixes provided by Vinoth. Closed: 5 Rejected: 1 |  | P1-6591
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1. Tested the performance of charts for May and June month 2. Validated Error Code, Current mode and ZC metrix data in MetricSummary_60mins table from Jan2025 to June2025 3. Tested ZC charts logic which fetches data from Metric summary table 4. Validated 7 issue fixes in New sunops 5. In JMeter, tested for 15 users at Portfolio and Site level for last 7 days and a 7 days period with different date ranges for 15 users and monitored the CPU utiliation and observed the memory usage Filed 2 issues |  | P1- 6592, 6593

## July25
| Week -27 | 30-06-2025 to 04-07-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Validated the issue fixes delivered by Harman team. 2.DID sanity testing in new sunops after fix for react upgrade is done 3.Tested the whole maintenance feature in new sunops as vinoth fixed issues in it. 4.Validated metric summary 60 mins table from Oct 2024 - Jan 2025. 5.Validated and closed the availability and positional accuracy occurences issues in their corresponding table. 6.Tested the whether zone mapping is done correctly for the extra devies in DID. |  | P1-6646
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Tested Downloads and Custom charts in New Sunops after the SSL configuration changes 2. Validated 2 issues related to Site maintenance and tested Site maintenance 3. Tested the zone and site mapping for those devices after adding extra devices from DID to devices cleanup table 4. Validated the MetricSummary_60mins table from Oct2024 to June2025 5. Validated the availability and uptimebase prepopulated table after getting fix for total occurence issue Validated 5 issues 6. In Sunops test server, tested the tracker if feature at the device level
| Week -28 | 07-07-2025 to 11-07-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Uploaded the asbuilt file for Lewis_NY project in SunDAT. 2.Validated the issue fixes related to historical performance and issue summary. 3.Tested GA fixes in SunDAT. 4.Tested tracker id feature in production sunops . 5.Tested the performance of downloads and overview APIs. 6.Uploaded the DID files for 4 sites and analysed the device mismatch between DID file and meta.devices table.
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Validated data in the pinot readings table, Availability, Uptimebase, Metric summary and Issue summary pre-populated tables for 12 months of data 2. Validated the performance issue fix in New Sunops 3. Validated 3 issue summary bug fix 4. In Sunops production, tested tracker id feature and executed sanity test cases. 5. Tested historical performance 6. Validated the data discrepancy issue fix in Issue summary and Metric summary table
| Week -29 | 14-07-2025 to 18-07-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 4days) = 32 leave on 14-07-2025 | 1.Tested the Salesforce changes in the SunDAT test server along with Pradeep. 2.Validated the performance of NewSunOps for May, June, and July, after the Harman team deleted and migrated segments with increased memory allocation. 3.Verified data retrieval from the cold tier. 4.Retested the closed bugs in NewSunOps and reopened two issues. 5.Prepared and shared the table and query documentation for NewSunOps with Jaya. 6.Received the final production build for NewSunOps on 18-07-2025. Performed end-to-end and performance testing on the build and provided the go-ahead for production sign-off to the Harman team.
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Tested the performance of New Sunops for May, June and July month in Overview, Downloads, Custom Charts, Error and Mode at the device level. 2. Performed regression testing in the New Sunops 3. Validated the Readings, Issue summary, Metric summary and Availability pre-populated tables 4. Prepared and shared the feature wise table and queries we used for our testing with Jaya. 5. Revalidated the closed bugs in New Sunops and reopened 2 issues 6. Validated the 2 reopened issues 7. Received the final production build for NewSunOps on 18-07-2025. Performed end-to-end, performance and Scalabiity testing on the build and provided the go-ahead for production sign-off to the Harman team.
| Week -30 | 21-07-2025 to 25-07-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1.Checked whether all the schedulars in pinot server are running continuously from 18th july to 21 july without any time out. 2.Noted down the performance of overview charts and downloads in newsunops for future reference. 3.Tested the tracker GA changes in SunDAT test server along with Pradeep. Received production Build in SunDAT production server .Tested the recent fixes in tracker GA and did one round of sanity testing.All are working fine in production server. 4.Uploaded DID files for seven sites and did the regular expression mapping for the zones in those sites. 5.After cluster restart,Did one round of sanity in newsunops and filed 1 issue. |  | P1-6745
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Checked the Pinot schedulers status and validated the tables 2. Added regular experession for recently uploaded sites to Commissioning table 3. Checked the Pinot performance of Overview, Downloads, Custom charts and notes it for future reference 4. Validated the Readings and Pre-populated tables after completion of Merge rollup task 5. Tested tracker GA in Sundat production 6. 7 new sites were started repprting to Sunops from June 2025, found the DID from Eygnyte , Uploaded them and regex for those sites 7. Validated the Pinot readings and pre-populated tables after the Cluster restart |  | P3- 6746
| Week -31 | 28-07-2025 to 01-08-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 4days) = 32 Comp-off on 28-07-2025 | 1.Tried uploading the southwick asbuilt file , but file is not getting uploaded into SunDAT. Compared southwick dwg files with other dwg files to seee whether any chages in the CAD file.Pile points are not marked as expected in the CAD file so reuested srini (sales team) to mark the pile points as expected. 2.Checked the samson site for 2023 data for wind speed metric and shared the updates to Jaya. 3.checked the schedulars in in pinot sunops. Availability and positional accuracy schedulars are not running line informed the same to Jaya. 4.Updated the data validation python script to handle forward filling and to take data directly from big query instead of uploading csv files.
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 4days) = 32 Comp-off on 01-08-2025 | 1. Checked whether any new devices have started reporting in all the DID uploaded sites (126 sites) 2. Analysed the sample Parquet file 3. Prepared Python script to validate data between BQ and Parquet. The validation process includes, Record Count Comparison and Value Comparison for each timestamp and metric 4. Added Python script to fetch BQ data directly from BQ server 5. Updated Python script to handle forward filling in Parquet 6. Checked the Zone mapping for 16 sites in meta.dcp_dup

## Aug25
| Week -32 | 04-08-2025 to 08-08-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Updated the data validation Python script to accommodate metrics from all 11 metric groups and validated it using sample data. 2. And, In the Parquet folder, the data is organized into separate folders for each zone and divided by date. So, we updated the script to read all zones from the particular date folder 3. Yash provoded a test build of Parquet version for ZC charts, Availability, Tracker Communication feature and tested it 4. Jaya asked us to download and share the latest schema and configuration of all the tables in the current Pinot server and preparing it 5. Compared the schema of all the 20 tables in the current Pinot server with the data store downloaded from Pinot shared by Jaya |  | P1- 1598 P2- 1599 1601
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Updated the data validation Python script to accommodate metrics from all 11 metric groups and validated it using sample data. 2. And, In the Parquet folder, the data is organized into separate folders for each zone and divided by date. So, we updated the script to read all zones from the particular date folder 3. Yash provoded a test build of Parquet version for ZC charts, Availability, Tracker Communication feature and tested it 4. Jaya asked us to download and share the latest schema and configuration of all the tables in the current Pinot server and preparing it 5. Compared the schema of all the 20 tables in the current Pinot server with the data store downloaded from Pinot shared by Jaya |  | P1- 1598 P2- 1600 1602
| Week -33 | 11-08-2025 to 15-08-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 4days) = 32 Holiday on: 15-08-2025 | 1.Compared the table/Schema config for 10 tables between data store and pinot server and shared the observation to Jaya 2.Got minio server access from Jaya. Downloaded AZ1 parquet files from Minio server. Validated sample parquet files from minio server 3.Tested below cases in data validarion : Device movement between zones Zone renaming forward filling and updated comments in bug_id-1598. 4.Compared the site_id between raw-data andOLAP data. Reported the missing sites to Anand. |  | P2-1603,1604
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 3days) = 24 Leave on: 12-08-2025 Holiday on: 15-08-2025 | 1. Compared the schema and configuration of 10 tables out of all the 20 tables in the current Pinot server with the data store and the shared the report with Jaya 2. Got MinIO access in remote machine and cross checked the raw bq data in MinIO for the group id’s file where we previously found a mismatch between Parquet and Bq 3. Validated the Parquet data for all 10 group IDs for Centerfield on 05-07-2025 and faced data is missing in BQ but present in Parquet issue also for AZ0, AZ1, AZ3 group_ids and updated in the issue 1598 4. Verified whether the zone renaming done in the cleanup table is reflected in the Parquet data 5. Checked the sites that are available in cleanup table and not in Minio server. |  | P2- 1605
| Week -34 | 18-08-2025 to 22-08-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 5days) =40 | 1.Validated the sample parquet files from minio server. 2.Validated the Average angle stat card in parquet Sunops. 3.Tested the New metric(Tracker performance metric) developed in current Sunops. 4. Validated the issue fixes in this new metric. 5.Tested the production build . 6.Tested the tracker performance metric in detailed summary report at portfolio level. 7. Checked the BQ raw data and the OLAP Parquet transfer file in MINIO, and prepared a script to identify missing site and group IDs in the OLAP Parquet |  | P2-1611,1612,1613,1607
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 5days) = 40 | 1. Validated the Parquet file for all the group id's for CO29 site for 05-07-2025. 2. Tested the average angle card at Site and Zone level in the Sunops parquet and prepared a python script to validate average angle 3. In current Sunops, tested a new metric Tracker Performance, tested it in the Summary card, Historical performance. 4. Validated the Tracker performance issue fixes 5. Tested the Tracker performance in production server 6. Tested the tracker performance metric in detailed report 7. Verified the BQ raw data and OLAP Parquet transfer file in MINIO, and prepared a script to check for missing site and group IDs in OLAP Parquet. |  | P2- 1606, 1609, 1610
| Week -35 | 25-08-2025 to 29-08-2025
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/SunOps | (8 hrsx 4days) =32 27-08-2025-holiday for Vinayagar chathurthi. | 1.Prepared python script to validate data between olap and bigquery bucket . 2.Validated test build from Yash for issue fix for the issue_ID 1613. 3.Completed data validation for the sites renamed in OLAP. 4.Tested GA in SunDAT after updating the credentials for salesforce. 5.Tested Sunops demo server . 6.Had call with Pradeep and Shipra (Sales team) regarding voyager GA not generating.
2 | Rasikapriya | SunDAT/SunOps | (8 hrsx 4days) =32 27-08-2025-holiday for Vinayagar chathurthi. | 1. Prepared a python script to check the missing group IDs for each site and date by comparing the BQ raw data and OLAP transfer files. 2. In the validation report of missing group id's in OLAP folder, filtered out the sites that were missing for all dates and available only in cleanup. And identified the sites that have data missing for specific dates and metric groups. 3. In the test server, validated the Something went wrong issue, and tested the tracker performance metric at all levels. 4. Validation the missing group_id in the sites that are renamed in cleanup. Six sites were renamed in OLAP and checked the missing group_id's in 3 sites. 5. Tested the Sunops demo server