## Index
Open issues
Priority | P0 | P1 | P2 | P3 | Total |  | Issue Classification | P1 | P2 | P3 | Total
Open | 9 | 70 | 34 | 1 | 114 |  | Pinot Query | 56 | 17 | 0 | 73
Closed |  | 41 | 36 | 7 | 84 |  | Performance /API timeout | 9 | 6 |  | 15
Total | 9 | 111 | 70 | 8 | 198 |  | UI | 2 | 8 | 1 | 11
[7 empty] | Pinot Schedular | 4 | 2 |  | 6
[7 empty] | Pinotquery/API | 2 |  |  | 2
[7 empty] | Segment Missing | 1 |  |  | 1
[7 empty] | UI/API | 5 | 1 |  | 6
[7 empty] | Total | 79 | 34 | 2 | 114
[6 empty] | Screen | Features | P1 | P2 | P3 | Total
[6 empty] | Overview | Summary table/card | 10 | 4 |  | 14
[7 empty] | Availability | 7 | 2 |  | 9
[7 empty] | Availability vs Error | 1 | 1 |  | 2
[7 empty] | Availability impact summary | 1 |  |  | 1
[7 empty] | Live cards | 1 | 3 | 1 | 5
[7 empty] | Error Summary, Mode Summary | 6 | 2 |  | 8
[7 empty] | Wind Speed, Wind Direction |  |  |  | 0
[7 empty] | Historical performance | 3 |  |  | 3
[7 empty] | Positional accuracy | 9 | 1 |  | 10
[7 empty] | All charts (Overview) | 1 | 2 |  | 3
[7 empty] | Issue Summary | 7 | 6 |  | 13
[7 empty] | Chart Performance | 1 | 2 |  | 3
[7 empty] | Data discrepancy | 2 |  |  | 2
[7 empty] | Overview total | 49 | 23 | 1 | 73
[6 empty] | Live status |  | 4 | 2 |  | 6
[6 empty] | Downloads |  | 9 | 5 |  | 14
[6 empty] | Custom Charts |  | 4 | 1 |  | 5
[6 empty] | Site maintenance |  | 3 |  |  | 3
[6 empty] | Pinot | Segment issue (Data discrepancy) | 1 | 1 |  | 2
[7 empty] | Readings table | 2 |  |  | 2
[7 empty] | New sites | 1 |  |  | 1
[7 empty] | Device movement (meta.device) | 6 | 2 |  | 8
[6 empty] | Total |  | 79 | 34 | 1 | 114

## Defects
Date | Build count | Builds released | Defect Count | Defect ID | Defect name | Priority | Critical P0 | Classification | Status | Feature/Label
Oct 1 - Oct 04 | 1 | Week40 | 5 | 5086 | Current Angle Summary value is incorrectly shown as 0 | P3 |  |  | Closed | Current Angle
|  |  |  | 5087 | Dropdown(site/zone/device) is not refreshing on changing the portfolio/site/zone. | P1 |  |  | Closed | UI
|  |  |  | 5088 | Data is shifted backward by 1 time interval | P1 |  |  | Closed | All Charts
|  |  |  | 5090 | Error and Mode filtering not applied at Zone and Site levels for trackers with multiple Errors and Modes | P1 |  | Pinot Query | Closed | Error Summary, Mode Summary
|  |  |  | 5116 | Wind Speed chart is not loading for APEX site. | P2 |  |  | Closed | Wind Speed
Oct 07 - Oct 11 | 1 | Week41 | 5 | 5117 | Data mismatch between New Sunops and Production Sunops for ZC and Current Angle Charts | P1 |  |  | Closed | Data discrepancy
|  |  |  | 5118 | For some sites extra row is displayed in Exported Wind Summary chart file | P3 |  | Pinot query | Closed | Wind Speed, Wind Direction
|  |  |  | 5119 | Error and Mode Summary Charts are not loading at Portfolio level | P1 |  |  | Closed | Error Summary, Mode Summary
|  |  |  | 5122 | Charts are not loading when more than 2 months is selected in date time picker | P2 |  |  | Closed | UI
|  |  |  | 5123 | Data missing and mismatch between Pinot and Big query | P1 |  |  | Closed | Data discrepancy
Oct 14 - Oct 18 | 1 | Week42 | 2 | 5137 | Zones are not listed in the "Zones" dropdown | P1 |  |  | Closed | UI
|  |  |  | 5136 | The loading cursor is not visible when the charts take time to load. | P2 |  |  | Closed | All Charts
Oct 21 - Oct 25 | 1 | Week43 | 11 | 5141 | Availability mismatch due to the availability shown as 0 instead of showing null during site outage | P1 |  | Pinot Query |  | Availability
|  |  |  | 5143 | At the site level, the availability average is incorrectly calculated as a normal average instead of a weighted average | P1 |  | Pinot Query | Closed | Availability
|  |  |  | 5144 | Alarm counts for all Zones incorrectly displayed as 0 in Site summary table | P1 | P0 | pinot query |  | Summary card/table
|  |  |  | 5145 | Availability Impact Summary Chart data not refreshing when changing Sites/Zones/Devices and sometimes not loading | P1 |  | UI | Closed | Availability
|  |  |  | 5146 | Mismatch in total Sites/Zones/Devices in Summary Card | P1 |  |  | Closed | Summary card/table
|  |  |  | 5148 | The portfolio summary card does not load when a period of more than 4 months is selected(from 01-06-2024) | P1 |  | Performance/apI timeout | Closed | Summary card/table
|  |  |  | 5150 | Last sent column in summary table is not updated it is showing last updated as > 30 days | P1 | P0 | Pinot Query |  | Summary card/table
|  |  |  | 5151 | Overview Summary API fails at Site level when selecting more than 3 months | P1 | PC | Performance/apI timeout |  | Summary card/table
|  |  |  | 5152 | Error count mismatch between QA and SunOps Production | P1 |  | Pinot query |  | Summary card/table
|  |  |  | 5153 | Incorrect values shown in Availability Impact Summary Chart | P1 |  | Pinot Query | Closed | Availability
|  |  |  | 5155 | Availability vs Errors Chart data is not matching with Summary table data | P1 |  | Pinot Query | Closed | Availability
Oct28 - Nov1 | 1 | Week44 | 20 | 5156 | Portfolio summary table is not refreshing while changing the portfolio | P1 |  |  | Closed | Summary card/table
|  |  |  | 5158 | Tracker Availability Card shows "No data" even though when data is available for last 7 days | P1 | P0 | pinot query |  | Live card
|  |  |  | 5195 | At the device level, all errors and modes should be displayed without any prioritization | P1 |  | pinot query | Closed | Error Summary, Mode Summary
|  |  |  | 5201 | Got something went wrong error when selecting a date in date time picker and navigating to Site /Zone | P1 |  |  | Closed | UI
|  |  |  | 5203 | Portfolio's are not listed in the portfolio dropdown | P1 |  |  | Closed | UI
|  |  |  | 5204 | At the portfolio level, the device count in Mode and Error Summary is lower in New Sunops than in Production. | P1 |  | Pinot Query |  | Error Summary, Mode Summary
|  |  |  | 5205 | Error should be prioritized at device , zone , site and portfolio level | P1 |  | Pinot Query | Closed | Error Summary
|  |  |  | 5206 | Data is missing in the Error and Mode Summary chart when the value is zero | P2 |  | Pinot query | Rejected | Error Summary, Mode Summary
|  |  |  | 5207 | At Portfolio and Site levels, Mode Summary, Error Summary and ZC Charts displays chart from selected time instead of next interval | P2 |  | Pinot query |  | All Charts
|  |  |  | 5208 | Custom charts are not populating | P1 |  |  | Closed | Custom Charts
|  |  |  | 5209 | When maintenance logs are added for a site/ zone, in the scope it is showing null for zone and device level | P2 |  |  | Closed | Site maintenance
|  |  |  | 5210 | For ongoing and not-started maintenance logs, the end date should be shown as 'TBD.' Currently, it is displayed as 'Invalid Date | P2 |  |  | Closed | Site maintenance
|  |  |  | 5211 | The newly created ongoing activity is not appearing under ongoing tab in the table view or in recent activities. | P2 |  |  | Closed | Site maintenance
|  |  |  | 5212 | End activity and remind me options should be enabled for ongoing activity. | P2 |  |  | Closed | Site maintenance
|  |  |  | 5213 | If an ongoing activity exceeds the 30-day limit, a '30 Days old' label should be displayed for that maintenance log. | P2 |  |  | Closed | Site maintenance
|  |  |  | 5214 | Got Something went wrong error when cloning a shared chart in Custom Charts | P1 |  |  | Closed | Custom Charts
|  |  |  | 5215 | The current user's shared chart is incorrectly displayed in their own "Select Shared Charts" list | P2 |  |  | Closed | Custom Charts
|  |  |  | 5216 | Not able to delete shared charts in Custom charts | P2 |  |  | Closed | Custom Charts
|  |  |  | 5217 | Calendar display overlaps snooze and cancel buttons in "Remind me on" notification for Site Maintenance | P3 |  |  | Closed | Site maintenance
|  |  |  | 5218 | Cards are not loading at Portfolio/Site/Zone/Device level | P1 |  |  | Closed | Cards
Nov4-Nov8 | 2 | Week45 | 19 | 5220 | In Site maintenance, job status and alerts are not shown in the notifications screen | P1 |  |  | Closed | Site maintenance
|  |  |  | 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | P1 |  | Pinot Query | Closed | Site maintenance
|  |  |  | 5227 | View devices button in not available in zone summary card. Overview_summary API is failing. | P1 |  |  | Closed | Summary card/table
|  |  |  | 5229 | Availability value increases even when the tracker operational status is set to "No" | P1 | P0 | Pinot Query |  | Site maintenance
|  |  |  | 5230 | Maintenance icon should shown in summary card ,indicating that the availability has been adjusted to account for the maintenance activity | P2 |  |  | Closed | Site maintenance
|  |  |  | 5231 | UTC time displayed instead of Site's time zone in Recent activities at Site/Zone/Device levels | P2 |  |  | Closed | Site maintenance
|  |  |  | 5232 | Availability incorrectly changes for other devices in the Zone when logging activity for a Single device | P1 | P0 | pinot query |  | Site maintenance
|  |  |  | 5236 | Able to end activity and set reminder for the logs created by other users | P2 |  |  | Closed | Site maintenance
|  |  |  | 5237 | Not able to login into QA server | P1 |  |  | Closed
|  |  |  | 5238 | Taking more time to load availability impact chart and Availability vs error chart | P2 |  | Performance/apI timeout |  | Availability
|  |  |  | 5242 | Cards are not loading at portfolio level | P1 |  | Performance/apI timeout | Closed | Live card
|  |  |  | 5243 | Tracker with error card is not working. | P1 |  | Pending functionality | Closed | Live card
|  |  |  | 5244 | Average angle and mode card is not loading .Average_angle and current_mode Api's are failing(inconsistent) | P2 |  | Pinot query | Closed | Live card
|  |  |  | 5245 | Charts are not loading when the date range selected includes Oct 26 to Oct 29 | P2 |  |  | Closed | All Charts
|  |  |  | 5246 | Incorrect alert message shown as activity added when ending an Ongoing activity in Site maintenance | P2 |  |  | Closed | Site maintenance
|  |  |  | 5247 | In the search field in breadcrumbs, if a device without a tracker ID is entered, it displays "null" in place of the tracker ID | P2 |  |  | Closed | UI
|  |  |  | 5248 | Data mismatch between Production and NewSunops due to inclusion of upper boundary timestamp in date filtering | P1 |  | Pinot Query |  | Data discrepancy
|  |  |  | 5249 | Device moved from one zone to another is not reflected in new sunops | P1 |  | Pinot Query schedular |  | meta.device
|  |  |  | 5250 | Zone and Device id shown as null in 30-day old ongoing activity reminder for Site and Zone level activity | P3 |  |  | Closed | Site maintenance
Nov11-Nov15 | 1 | Week46 | 13 | 5252 | Device count mismatch in mode summary chart when one hour ,30 mins,15 min,10 mins and 5 mins interval. | P1 | PC | Pinot Query |  | Mode Summary
|  |  |  | 5274 | Custom Chart with Total RC value type shows device count incorrectly as 0 or 1 | P1 |  | Pinot Query |  | Custom Charts
|  |  |  | 5275 | Custom Chart with Total RC value type display chart for incorrect date/time range instead of selected range | P1 |  | Pinot query |  | Custom Charts
|  |  |  | 5277 | When notes are not provided for a maintenance activity, double quotes should not appear in the card or table views | P3 |  |  | Closed | Site maintenance
|  |  |  | 5278 | In custom charts, "No Data Available" should not appear while charts are loading and loading cursor should be displayed | P2 |  |  | Closed | Custom Charts
|  |  |  | 5281 | Not able to add multiple shared charts to a dashboard simultaneously | P2 |  | UI | Rejected | Custom Charts
|  |  |  | 5282 | Value mismatch in Custom charts between New SunOps and Production for "Recent" and "First" value types | P2- FTC |  | Known issue |  | Known issue
|  |  |  | 5283 | Able to access Hail Settings by directly navigating to the URL, even when disabled for user profile | P1- FTC |  | Known issue |  | Known issue
|  |  |  | 5284 | Diffuse feature is not available in new sunops | P2- FTC |  | Known issue |  | Known issue
|  |  |  | 5285 | Latitude and longitude fields incorrectly display the value "-infinity" for sites with empty values | P3- FTC |  | Known issue |  | Known issue
|  |  |  | 5286 | Changes made to the hail settings are not being saved in new sunops | P2- FTC |  | Known issue |  | Known issue
|  |  |  | 5287 | In the Notification section, release notes are displayed without the "View Details" button | P3 |  |  | Closed | Release notes
|  |  |  | 5292 | Charts and cards were not loading in QA server due to segment missing issue in pinot. | P1 |  | segment missing | Closed | All Charts and Cards
Nov18-Nov22 | 4 | Week47 | 20 | 5299 | In Live Status, filters in column headers are not working | P2 |  |  | Closed | Live status
|  |  |  | 5300 | CSV Download option is not available on the live status screen | P2 |  |  | Closed | Live status
|  |  |  | 5302 | Got TypeError when clearing the search in Live status screen | P2 |  |  | Closed | Live status
|  |  |  | 5303 | Unhandled Rejection (TypeError): Occurs when selecting a site on the Live Status screen after navigating from the Overview page | P2 |  |  | Closed | Live status
|  |  |  | 5307 | error,mode,wind speed and direction in over view page are failing when date range of Nov01-18 is selected | P2 |  | Performance/apI timeout |  | Performance
|  |  |  | 5308 | For Miacomet site, at zone level no data is showing up in live status screen | P2 |  | Pinot Schedular |  | Live status
|  |  |  | 5309 | Performance issue: Charts are taking more time to load | P1 |  | Performance/apI timeout |  | Performance
|  |  |  | 5310 | Exported file in view and downloads displays Production Sunops data instead of New Sunops data | P1 |  |  | Closed | Downloads
|  |  |  | 5311 | For pvVoltage and batteryVoltage metrics for each zone it is displaying an extra column like (Zone_id/ZC) | P2 |  | UI/API |  | Downloads
|  |  |  | 5312 | For RC and ZC metrics, some data is missing at Portfolio/Site level but visible at Site/Zone level in view and download | P1 |  | Pinot Query |  | Downloads
|  |  |  | 5313 | Values are not showing for some RC_alerts in direct downloads.(both consolidated and individual downloads) | P1 | PC | Pinot Query |  | Downloads
|  |  |  | 5320 | Mismatch in zones communicating card at portfolio level. | P1 | P0 | Pinot Query |  | Live card
|  |  |  | 5319 | For Harts Mill site , only one device is showing up in the live status screen. | P1 |  | Pinot Query | Closed | Live status
|  |  |  | 5314 | In live status , Failed to fetch realtime dataRequest failed with status code 500(inconsistently) | P1 |  | Performance/apI timeout | Rejected | Live status
|  |  |  | 5315 | In live status ,facing Request failed with status code 500 for Lick creek site | P2 |  |  | Closed | Live status
|  |  |  | 5318 | In live status, Showing negative seconds in last updated field | P1 |  | Pinot Query |  | Live status
|  |  |  | 5323 | Download API in Direct Downloads fails with a 500 status code when there is no data available for the selected metrics | P1 |  | Pinot query |  | Downloads
|  |  |  | 5324 | At portfolio level, the Download API in Direct Downloads fails with a 500 status code even when data exists for the selected metrics | P1 | PC | Performance/apI timeout |  | Downloads
|  |  |  | 5325 | At the portfolio and site level, data in view and downloads starts showing from the selected interval instead of the next interval | P2 |  | Pinot query |  | Downloads
|  |  |  | 5326 | There is mismatch in values in direct downloads for all aggregation type and metric | P1 | PC | Pinot Query |  | Downloads
Nov25-Nov29 | 2 | Week48 | 15 | 5329 | Device ID (DID) in the Live Status page is displayed in two lines instead of a single line | P2 |  |  | Closed | Live status
|  |  |  | 5330 | In the live status, the alert column filter is displaying alerts that have not occurred on the selected site | P2 |  |  | Closed | Live status
|  |  |  | 5331 | At portfolio level , not able to navigate from user analytics to overview screen | P2- FTC |  | Known issue |  | Known issue
|  |  |  | 5332 | In Pinot, Availability 30 mins table have data only till Oct 16th | P1 |  | Pinot Query schedular | Closed | Availability
|  |  |  | 5333 | In live status screen , no data is shown for most of the sites on 26-11-2024 | P1 |  | Pinot Query | Closed | Live status
|  |  |  | 5334 | Availability mismatch between New Sunops and Production due to last reported date of Site/Zone/Device | P1- FTC |  | Known Issue |  | Known issue
|  |  |  | 5335 | Tracker Availability metric value is shown as 0 in Downloads due to API failure with status code 500 | P1 |  | Pinot query |  | Downloads
|  |  |  | 5338 | Direct download is taking more time to fetch data in New SunOps compared to Production | P2 |  | Performance/apI timeout |  | Downloads
|  |  |  | 5341 | Mismatch in device count(between production and new sunops) in portfolio summary table for some sites. | P1 | PC | Pinot Query schedular |  | Summary card/table
|  |  |  | 5343 | Live status columns in New SunOps should match the order in Production | P2 |  | UI | Closed | Live status
|  |  |  | 5344 | In the summary card, when the overview_summary API is pending, the site/zone/device count should not be shown | P2 |  |  | Closed | Summary card/table
|  |  |  | 5345 | In the notification, clicking View Details for a specific release should display only the release notes related to that particular production release | P2 |  |  | Closed | Notification
|  |  |  | 5346 | In view and downloads, data_table API fails with data transformation error for errorcode metric. | P1 |  | Pinotquery/API |  | Downloads
|  |  |  | 5347 | In direct downloads ,selected metrics is errorcode but in downloaded file it is showing active_power metric. | P2 |  | UI |  | Downloads
|  |  |  | 5349 | In View and downloads for ZC alerts (pvVoltage and batteryVoltage), instead of displaying binary values (0's and 1's), the actual voltage values are being shown. | P2 |  | Pinot query |  | Downloads
Dec2-Dec6 | 1 | Week49 | 5 | 5362 | When a log is entered for a site, it is showing maintenance card and icon for the zones/devices of other sites due to cache issue. | P2 |  |  | Closed | Site maintenance
|  |  |  | 5363 | Loading cursor should be shown in Total Sites/Zones/RCs and View Sites/Zones/RCs when fetching data | P2 |  |  | Closed | Summary card/table
|  |  |  | 5365 | The availability value does not update immediately when a maintenance activity is added or ended | P2 |  |  | Closed | Site maintenance
|  |  |  | 5366 | Merge Response error occurs while querying Readings_2 table in Pinot | P2 |  | Known issue | Closed | Known issue
|  |  |  | 5367 | APIs in overview page is failing inconsistently | P2 |  | Performance/apI timeout |  | Summary card/table
Dec9-Dec13 | 2 | Week50 | 13 | 5374 | The device is in Auto mode, but in the availability versus error chart, it is incorrectly displayed as IDLE mode | P1 |  | UI | Closed | Availability vs error
|  |  |  | 5375 | Zone IDs are sorted in lexicographical order instead of numerical order | P2 |  | Pinot query |  | Summary card/table
|  |  |  | 5377 | Availability vs Error chart is not loading at Device level | P1 | P0 | Pinot query |  | Availability vs error
|  |  |  | 5378 | When the overview API is pending , availability versus error and impact summary chart should be shown in UI with loading cursor. | P2 |  | UI | Closed | Availability vs error, Availability impact summary
|  |  |  | 5388 | In pinot devices table, it is showing the end_datetime and last_updated_at as 1970-01-01 00:00:00.0 | P2 |  | Pinot query |  | Pinot
|  |  |  | 5389 | Incorrect error count is shown at the Portfolio level for all sites | P1 |  | Pinot query |  | Summary card/table
|  |  |  | 5390 | In Summary card, view sites is displayed instead of View zones/devices at Site and Zone levels while summary table loading | P3 |  | UI | Closed | Summary card/table
|  |  |  | 5401 | Showing wrong mode in availability versus error chart | P2 |  | Pinot query |  | Availability vs error
|  |  |  | 5402 | Availability is showing as 100 % when the site is at outage | P1 |  | Pinot query |  | Availability
|  |  |  | 5403 | In Availability charts, Availability value incorrectly shown as 'No Data' and Empty for Zones/RCs with No Data and charts are not displayed | P1 |  | UI | Closed | Availability vs error, Availability impact summary
|  |  |  | 5404 | For Miacomet site, availability average is showing as "No Data" for December 03,04 and 05 | P1 |  | Pinot query | Closed | Availability
|  |  |  | 5405 | Error 427 in Availability 30mins table due to unresponsive pinot server (Inconsistent) | P2 |  | Pinot query |  | Availability
|  |  |  | 5408 | Progress bar should be shown for live cards even when there is No data | P3 |  | UI |  | Live cards
Dec16-Dec20 | 1 | Week51 | 11 | 5409 | tracker_id column is not updated for the devices in Pinot devices table. | P1 | P0 | Pinot query |  | meta.device
|  |  |  | 5410 | For Chomongonday site, mismatch between total number of records in devices table between NewSunops and Production sunops | P1 | P0 | Pinot query |  | meta.device
|  |  |  | 5411 | diffuse_disabled column is updated as false instead of NULL in Pinot. | P1 |  | Pinot query |  | meta.device
|  |  |  | 5412 | Mismatch in total device count in tracker with error card. | P2 |  | Pinot query |  | Live cards
|  |  |  | 5414 | Duplicate device entries in Devices table in Pinot for Samson site even though the device remains in the same zone/site | P2 |  | Pinot query |  | meta.device
|  |  |  | 5426 | In zone communicating card , count of zones communicating is higher than total zones | P2 |  | Pinot query |  | Live cards
|  |  |  | 5427 | In Zones communicating card, communicating zone count (numerator) is empty.(Inconsistent) | P2 |  | Pinot query |  | Live cards
|  |  |  | 5428 | In zone communicating card, total zone count in the denominator should not be changed when no new zone is added | P2 |  | Pinot query |  | Live cards
|  |  |  | 5429 | Newly added sites in Production (Short Sands, Sevior, Seneca Gardens) are not shown in New SunOps | P1 | P0 | Pinot query |  | New sites
|  |  |  | 5430 | Future dates displayed in datetime_30min, registration_date, and timestamp_30min columns in availability_30mins table | P2 |  | Pinot query | Closed
|  |  |  | 5431 | The Availability table contains data only up to December 8th because the availability scheduler has not been executed on daily basis | P1 |  | Pinot Query schedular |  | Availability
Dec30-Jan3 |  | Week52 | 2 | 5438 | For November and December, ZC charts are not loading when selecting a date range of more than 15 days, with a timeout execution error in Pinot | P2 |  | Pinot query | Closed | ZC Charts
|  |  |  | 5448 | Selected time interval in error summary chart is 12 hrs but it is showing data for 6 hours interval in chart. Issue is seen for 1 day interval also | P1 | P0 | Pinot query |  | Error summary
Jan6-Jan10 | 2 | Week2 | 8 | 5449 | Data missing in Readings_3 table for some sites | P1 |  | Pinot query | Closed | Data discrepancy
|  |  |  | 5450 | At site level, the device count decreases or data is not displayed for some days in the Mode Chart for larger date ranges in all time intervals | P1 | P0 | Pinot query |  | Mode summary
|  |  |  | 5451 | Data shifted backward by 1 day in Overview charts for 1 day interval | P2 |  | Pinot query |  | All charts
|  |  |  | 5452 | Devices which are not reporting for more than 90 days are not showing up in devices table | P1 | P0 | Pinot query |  | meta.devices
|  |  |  | 5456 | Device count in error/mode summary chart is decreased on selecting wide date range | P1 | P0 | Pinot query |  | Error Summary, Mode Summary
|  |  |  | 5457 | Mismatch in decimal value shown for error code metric in BQ and pinot | P1 |  | Pinot query |  | Error summary
|  |  |  | 5466 | Getting page unresponsive error in pinot server (51.8.41.190:9000) while fetching more than 7 lakh records. | P1 |  | Pinot query |  | Pinot
|  |  |  | 5467 | Data Discrepancy: Some Records are missing in the New Pinot (51.8.41.190) | P1 |  | Pinot query | Closed | Pinot
Jan13-Jan17 | 3 | Week3 | 27 | 5469 | Duplication of records in pinot | P1 |  | Pinot query |  | Pinot
|  |  |  | 5474 | In the downloads, the date in the timestamp column is showing as an invalid date | P1 |  | API | Closed | Downloads
|  |  |  | 5475 | Got unhandled rejection error inconsistently while selecting Sites/Zones | P2 |  | UI | Closed | Summary card/table
|  |  |  | 5479 | Api's are failing in production url. | P1 |  | API |  | All Charts and Cards
|  |  |  | 5480 | In Historical performance, the date is incorrectly shown as 1st Jan for all dates | P1 |  | UI | Closed | Historical performance
|  |  |  | 5481 | Mismatch in positional accuracy last 7 days card between production and newsunops. | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5482 | Data missing in Readings table for January and March in Sunfarm, Alkali and Twittys Creek sites | P2 |  | Pinot query |  | Data discrepancy
|  |  |  | 5483 | The overview charts are taking more time to load and it is failing inconsistently even at the site level | P2 |  | Performance/apI timeout |  | Performance
|  |  |  | 5486 | In the Availability_24hours table, data is not available for the 3 months from September to November | P1 |  | Pinot Query schedular | Closed | Availability
|  |  |  | 5488 | In the Positional accuracy table, data is not available for 6 months from January to June - No data from Jan to March | P1 | PC | Pinot Query schedular |  | Positional accuracy
|  |  |  | 5490 | Historical performance is not loading at device level | P1 | PC | Performance/apI timeout |  | Historical performance
|  |  |  | 5492 | Timestamp mismatch in positional accuracy 24 hours table between BQ and pinot | P1 |  | Pinot query |  | Positional accuracy
|  |  |  | 5493 | Custom charts API fails when creating a chart with the Total RC aggregation type | P1 | P0 | Performance/apI timeout |  | Custom Charts
|  |  |  | 5494 | Mismatch in value for uptime between BQ and pinot | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5498 | API Request failed with 500 error when adding a log in Site Maintenance | P1 | P0 | API |  | Site maintenance
|  |  |  | 5499 | uptimebase_24hours table has no data for last day of July, September, October and November month | P2 |  | Pinot Query schedular |  | Positional accuracy
|  |  |  | 5500 | The uptimebase_24hours table lacks data when positional accuracy is not calculated | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5501 | There is a significant difference in positional accuracy values between Production and NewSunOps. | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5502 | Device count is multiplied by date and displays incorrect count | P1 | P0 | Pinot query |  | Summary card/table
|  |  |  | 5503 | In Availability_24hours table, data is not available for some sites | P1 | P0 | Pinot query |  | Availability
|  |  |  | 5504 | Significant difference in availability value at device and zone level | P1 |  | Pinot query |  | Availability
|  |  |  | 5505 | Some devices are missing in zone summary table. | P2 |  | Pinot query |  | Summary card/table
|  |  |  | 5506 | It is showing positional accuracy as zero for all sites from March to June | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5507 | Availability average in Summary card should match with average of Availability in Historical Performance | P1 | P0 | Pinot query |  | Availability
|  |  |  | 5508 | During site outage, the historical performance chart should display "No Data" for both availability and positional accuracy | P1 | P0 | Pinot query |  | Historical performance
|  |  |  | 5509 | In Historical performance, the Availability and Accuracy not showing 0 and No Data during Zone Outage without Site Outage | P1 | P0 | Pinot query |  | Historical performance
|  |  |  | 5510 | Summary Card and Availability Charts keep loading when no tracker is available in the Site/Zone and last reported date is >60days | P2 |  | Pinot query |  | Summary card/table
|  |  |  | 5513 | Lower error count shown at Site and Portfolio levels when selecting a wide date range | P1 | P0 | Pinot query |  | Summary card/table
|  |  |  | 5514 | In the Availability impact chart, data is not shown for some sites/zones/devices even though they have availability impact values | P1 |  | Pinot query |  | Availability impact
Jan20-Jan24 | 0 | Week4 | 4 | 5528 | Analysisuptime is calulated considering record at maximum timestamp in the 30 mins interval. | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5530 | Mode Summary API is failing at Portfolio level when selecting a 1 hour time interval for a 1 year date range | P2 |  | API |  | Mode summary
|  |  |  | 5531 | Some devices are missing in Pinot devices table for Samson site | P1 |  | Pinot query |  | Devices table
|  |  |  | 5533 | Mismatch in positional accuracy between newsunops and production due to data coming late | P2- FTC
Jan27-Jan31 | 2 | Week5 | 13 | 5536 | Charts are taking more than 1min to load for last 7 days and live card APIs are failing | P1 |  | Performance/apI timeout |  | All charts
|  |  |  | 5540 | Issue_summary API is failing at site, zone and device level. | P1 |  | API | Closed | Issue summary
|  |  |  | 5541 | Overview Summary API is failing at Portfolio level | P1 | P0 | API |  | Summary card/table
|  |  |  | 5544 | Issue Summary API fails at specific date ranges | P1 | P0 | API |  | Issue summary
|  |  |  | 5545 | In Issue Summary, data is not shown in Row ID column at Zone level | P1 |  | UI |  | Issue summary
|  |  |  | 5546 | In Issue summary, the occurrences of an error are only displayed if their start date falls within the selected date range. | P1 | P0 | Pinot query |  | Issue summary
|  |  |  | 5547 | It is showing more than one row for same 30 min timestamp in uptimebase_30mins | P1 | P0 | Pinot query |  | Positional accuracy
|  |  |  | 5548 | UI issues in issue summary | P2 |  | UI |  | Issue summary
|  |  |  | 5555 | Issue which occurred for less than one hour should not be shown at portfolio level. | P1 | P0 | Pinot query |  | Issue summary
|  |  |  | 5561 | Overview summary availability, Overview summary and Issue summary APIs fail when the Site is at outage | P1 | P0 | Pinotquery/API |  | Summary card/table
|  |  |  | 5562 | The site is not at outage but in the availability table it is showing 1 for outage_count for all occurrences | P1 | P0 | Pinot query |  | Availability
|  |  |  | 5563 | The sum of the Availability Avg and Availability Impact should be close to 100% | P1 |  | Pinot query |  | Issue summary
|  |  |  | 5568 | At the portfolio level, the issue summary takes more time to load and sometimes the API fails | P1 | P0 | Performance/apI timeout |  | Issue summary
Feb3-Feb7 | 1 | Week6 | 8 | 5571 | History of the non reporting trackers are not showing in the issue summary. | P1 |  | Pinot query |  | Issue summary
|  |  |  | 5575 | In Downloads, the API fails with status code 500 when selecting Positional accuracy and Error code metric | P1 | P0 | API |  | Downloads
|  |  |  | 5576 | Custom charts which were created earlier got deleted automatically on every new test build | P1 | PC | UI |  | Custom Charts
|  |  |  | 5577 | Data missing in pinot for January 2025 | P1 | P0 | segment missing |  | Data discrepancy
|  |  |  | 5579 | Issue summary keep showing previous data when API is fetching new data | P2 |  | UI |  | Issue summary
|  |  |  | 5581 | In downloads , data is missing in table view when changing the time interval. | P1 | P0 | Pinot query |  | Downloads
|  |  |  | 5587 | In Live status , it is showing the older data | P1 |  | Pinot query |  | Live status
|  |  |  | 5589 | Incorrect outage Recommendation shown at Device level when Site is at outage | P2 |  | UI |  | Issue summary
Feb10-Feb14 |  | Week7 | 3 | 5606 | Zone bq connect recommendation is shown instead of Zone general outage | P2 |  | UI |  | Issue summary
|  |  |  | 5607 | Zone System Storage recommendation is shown instead of Zone bq connect | P2 |  | UI |  | Issue summary
|  |  |  | 5609 | Grammar mistakes in recommendations | P2 |  | UI |  | Issue summary

## BuildDetails
Build Date | Feature/Bug ID | Description | Testing Status
27/09/2024 | 1487 | Zone controller Sensor Summary Charts : [Wind, Speed, Wind Direction, Snow fall, Flood level] - React, Flask, Pinot changes | On progress
| 4801 | Modes Summary Chart : React, Flask, Pinot changes | On progress
| 4805 | Error Summary Chart : React, Flask, Pinot changes | On progress
2024-01-10 | 4803 | Current Angle Summary : React, Flask, Pinot changes | On progress
2024-07-10 | 5087 | Dropdown(site/zone/device) is not refreshing on changing the portfolio/site/zone. | Validated and rejected
14/10/2024 |  | 1 year of data migrated to Readings table | Data missing issue is seen
22/10/2024 |  | Availability (Summary card, Availability Impact Summary, Availability vs Error, Tracker availability, Zones Communicating, Trackers with Error, Mode, Average angle) | Only Summary Card and Summary Table is working
| 5137 | Zones are not listed in the "Zones" dropdown | Closed
29/10/2024 | 5090 | Error and Mode filtering not applied at Zone and Site levels for trackers with multiple Errors and Modes | Rejected and blocker 5195, 5205
30/10/2024 |  | Custom charts, and Availability with site maintenance | Functionality is Not working for both Custom charts and Site maintenanc
| 5087 | Dropdown(site/zone/device) is not refreshing on changing the portfolio/site/zone. | Closed
| 5088 | Data is shifted backward by 1 time interval | Closed
| 5119 | Error and Mode Summary Charts are not loading at Portfolio level | Closed
| 5122 | Charts are not loading when more than 2 months is selected in date time picker | Closed
2024-05-11 | 5208 | Custom charts are not populating | Not working and rejected
|  | Site maintenance functionality | On progress
2024-06-11 | 5123 | Data missing and mismatch between Pinot and Big query (Tested for 1 year) | Validated for 1year and working fine
| 5195 | At the device level, all errors and modes should be displayed without any prioritization | Not working and rejected
| 5203 | Portfolio's are not listed in the portfolio dropdown | Closed
| 5209 | When maintenance logs are added for a site/ zone, in the scope it is showing null for zone and device level | Closed
| 5210 | For ongoing and not-started maintenance logs, the end date should be shown as 'TBD.' Currently, it is displayed as 'Invalid Date | Closed
| 5211 | The newly created ongoing activity is not appearing under ongoing tab in the table view or in recent activities. | Closed
| 5212 | End activity and remind me options should be enabled for ongoing activity. | Closed
| 5213 | If an ongoing activity exceeds the 30-day limit, a '30 Days old' label should be displayed for that maintenance log. | Closed
| 5218 | Cards are not loading at Portfolio/Site/Zone/Device level | Closed
| 5227 | View devices button in not available in zone summary card. Overview_summary API is failing. | Closed
| 5231 | UTC time displayed instead of Site's time zone in Recent activities at Site/Zone/Device levels | Not working and rejected
| 5236 | Able to end activity and set reminder for the logs created by other users | Closed
|  | 60 mins live cards (Tracker with Errors, Average angle, Mode) and Live injection | Trackers with Errors not working
13/11/2024 | 5141 | Availability mismatch due to the availability shown as 0 instead of showing null during site outage | Not working and rejected
| 5156 | Portfolio summary table is not refreshing while changing the portfolio | Closed
| 5206 | Data is missing in the Error and Mode Summary chart when the value is zero | Not working at error summary and rejected
| 5214 | Got Something went wrong error when cloning a shared chart in Custom Charts | Not working and rejected
| 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | Not working and rejected
| 5230 | Maintenance icon should shown in summary card ,indicating that the availability has been adjusted to account for the maintenance activity | Not working and rejected
| 5247 | In the search field in breadcrumbs, if a device without a tracker ID is entered, it displays "null" in place of the tracker ID | Not working and rejected
| 5250 | Zone and Device id shown as null in 30-day old ongoing activity reminder for Site and Zone level activity | Closed
| 5208 | Custom charts are not populating | Closed
18/11/2024 | 5231 | UTC time displayed instead of Site's time zone in Recent activities at Site/Zone/Device levels | Closed
| 5247 | In the search field in breadcrumbs, if a device without a tracker ID is entered, it displays "null" in place of the tracker ID | Closed
| 5277 | When notes are not provided for a maintenance activity, double quotes should not appear in the card or table views | Not working and rejected
| 5420 | Live status feature | On progress
19/11/2024 |  | Downloads feature | On progress
2024-11-20 | 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | Not working and rejected
| 5274 | Custom Chart with Total RC value type shows device count incorrectly as 0 or 1 | Not working and rejected
| 5302 | Got TypeError when clearing the search in Live status screen | Closed
| 5246 | Incorrect alert message shown as activity added when ending an Ongoing activity in Site maintenance | Closed
| 5300 | CSV Download option is not available on the live status screen | Closed
2024-11-21 | 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | Not working and rejected
25/11/2024 | 5133 | Querying in pinot issue windows cache
| 5134 | Data Mismatch between Pinot and Big query in QA environment
| 5135 | Custom chart UI issue with more templates
| 5136 | The loading cursor is not visible when the charts take time to load. | Closed
| 5146 | Mismatch in total Sites/Zones/Devices in Availability Summary Card | Not working and rejected
| 5147 | Missing segment when running the query in Pinot QA Env | Working fine, need to check
| 5201 | Got something went wrong error when selecting a date in date time picker and navigating to Site /Zone | Closed
| 5228 | Getting Error Code: 200 when running Error Summary for greater ingestion_date range in pinot QA Env
| 5277 | When notes are not provided for a maintenance activity, double quotes should not appear in the card or table views | Closed
| 5278 | In custom charts, "No Data Available" should not appear while charts are loading and loading cursor should be displayed | Closed
| 5294 | Live Status UI issue: Overlapping of site and zone name
| 5299 | In Live Status, filters in column headers are not working | Closed
| 5314 | In live status , Failed to fetch realtime dataRequest failed with status code 500(inconsistently) | Not working, need to check tomorrow
28/11/2024 | 5146 | Mismatch in total Sites/Zones/Devices in Availability Summary Card | Closed
| 5214 | Got Something went wrong error when cloning a shared chart in Custom Charts | Not working and rejected
| 5217 | Calendar display overlaps snooze and cancel buttons in "Remind me on" notification for Site Maintenance | Closed
| 5220 | In Site maintenance, job status and alerts are not shown in the notifications screen | Closed
| 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | Not working and rejected
| 5281 | Not able to add multiple shared charts to a dashboard simultaneously | Not working and rejected
| 5303 | Unhandled Rejection (TypeError): Occurs when selecting a site on the Live Status screen after navigating from the Overview page | Closed
| 5329 | Device ID (DID) in the Live Status page is displayed in two lines instead of a single line | Closed
| 5310 | Exported file in view and downloads displays Production Sunops data instead of New Sunops data | Closed
2024-04-12 | 5214 | Got Something went wrong error when cloning a shared chart in Custom Charts | Closed
| 5226 | Maintenance log card is not showing on the overview page after adding a maintenance activity. | Closed
| 5230 | Maintenance icon should shown in summary card ,indicating that the availability has been adjusted to account for the maintenance activity. | Closed
| 5314 | In live status , Failed to fetch realtime dataRequest failed with status code 500(inconsistently) | Not working and rejected
| 5315 | In live status ,facing Request failed with status code 500 for Lick creek site | Closed
| 5333 | In live status screen , no data is shown for most of the sites . | Closed
| 5344 | In the summary card, when the overview_summary API is pending, the site/zone/device count should not be shown. | Closed
| 5345 | In the notification, clicking View Details for a specific release should display only the release notes related to that particular production release. | Closed
2024-11-12 | 5145 | Availability Impact Summary Chart data not refreshing when changing Sites/Zones/Devices and sometimes not loading | Closed
| 5153 | Incorrect values shown in Availability Impact Summary Chart | Closed
| 5155 | Availability vs Errors Chart data is not matching with Summary table data | Closed
| 5330 | In the live status, the alert column filter is displaying alerts that have not occurred on the selected site | Closed
| 5363 | Loading cursor should be shown in Total Sites/Zones/RCs and View Sites/Zones/RCs when fetching data | Closed
2024-12-12 | 5343 | Live status columns in New SunOps should match the order in Production | Closed
| 5374 | The device is in Auto mode, but in the availability versus error chart, it is incorrectly displayed as IDLE mode | Closed
| 5378 | When the overview API is pending , availability versus error and impact summary chart should be shown in UI with loading cursor. | Closed
| 5390 | In Summary card, view sites is displayed instead of View zones/devices at Site and Zone levels while summary table loading | Closed
| 5243 | Tracker with error card is not working. | Closed
19/12/2024 | 5403 | In Availability charts, Availability value incorrectly shown as 'No Data' and Empty for Zones/RCs with No Data and charts are not displayed | Closed
| 5408 | Progress bar should be shown for live cards even when there is No data | Rejected (Still Not shown for Tracker availability card)
26/12/2024 |  | Readings_3 (ZC Charts)
2025-03-01 | 5206 | Data is missing in the Error and Mode Summary chart when the value is zero | Rejected
| 5090 | Error and Mode filtering not applied at Zone and Site levels for trackers with multiple Errors and Modes | Closed
| 5195 | At the device level, all errors and modes should be displayed without any prioritization | Closed
Readings_3 (Error and Mode Charts)
2025-09-01 |  | New Pinot Env
13/1/2025 |  | Data missing fix
Positional Accuracy
Historical Performance
15/01/2025 |  | API failure fix
| 5480 | In Historical performance, the date is incorrectly shown as 1st Jan for all dates | Closed
16/01/2025 | 5486 | In the Availability_24hours table, data is not available for the 3 months from September to November | Closed
| 5488 | In the Positional accuracy table, data is not available for 6 months from January to June | Closed
28/01/2025 | 5207 | At Portfolio and Site levels, Mode Summary, Error Summary and ZC Charts displays chart from selected time instead of next interval | Rejected
| 5365 | The availability value does not update immediately when a maintenance activity is added or ended | Not able to test due to API failure
| 5399 | Incorrect values displayed in registration_date, registration_date_ts and interval timestamp columns in Pinot Readings table
| 5402 | Availbility is showing as 100 % when the site is at outage. | Not able to validate due to 5507 and 5510
| 5431 | The Availability table contains data only up to December 8th because the availability scheduler has not been executed on daily basis. | In 24hrs table, data available only till Jan 4th
| 5499 | uptimebase_24hours table has no data for last day of July, September, October and November month | Rejected
| 5503 | In Availability_24hours table, data is not available for some sites | Issue still seen
| 5504 | Significant difference in availability value at device and zone level | Issue still seen
| 5507 | Availability average in Summary card should match with average of Availability in Historical Performance | Rejected
| 5510 | Summary Card and Availability Charts keep loading when no tracker is available in the Site/Zone | Rejected
Positional Accuracy null fix
29/01/2025 | 5540 | Issue_summary API is failing at site, zone and device level. | Closed
2025-03-02 | 5474 | In the downloads, the date in the timestamp column is showing as an invalid date