## Nov24
Weekly Status Report
| Week -47 | 18-11-2024 to 22-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8hrs x 5days) = 40 | In Sundat, tested basic sanity for the new server. Executed sanity automation suite in new sundat server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 6 Filed defects count: 12 |  | P1- 5308, 5307, 5303, 5310,5311,5312,5313,5320,5319,5314,5318 P2- 5315
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 3days) = 24 | In Sundat, tested basic sanity for the new server. In Sunops, Tested Live status, performance testing for charts, Downloads and validated bug fixes. No of defects validated: 4 Filed defects count: 8 |  | P1- 5310, 5312, 5323, 5324 P2- 5299, 5300, 5302, 5325
| Week -48 | 25-11-2024 to 29-11-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Tested important features in SunDAT after deploying in azure server 2.In NewSunops, tested live status and downloads features. 3.Validated the issues fixes delivered by Harman team. .No.of defects validated:8 No of defects filed :9
P1-5314 p2-5330,5331,5333, 5344,5345,5346,5347, 5349
2 | Rasikapriya | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | Features tested, Filed defects count, Number od defects validated,Number of test cases written/updated
Defect ID of Defects with priority(P0,P1…)

## Dec24
| Week -49 | 02-12-2024 to 06-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validated the issue fixes . No.of defects validated-8 No of defects filed - 2 2.Analysed the extra timestamp columns added for different time intervals in Readings_2 table 3.Tested SunDAT after changing the dbabi and jsapi. |  | P2-5362,188637191,5367
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.In New Sunops, Validated the issue fixes . No.of defects validated- 8 No of defects filed - 3 2. Tested the Readings_2 table in Pinot and analyzed the additional timestamp columns added for different time intervals 3. Updated test cases for Custom charts and Site maintenance 4.Tested SunDAT after changing the dbabi and jsapi. | Custom charts- 14 Site maintenance- 44 | P2- 5363, 5366, 5367
| Week -50 | 08-12-2024 to 13-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops
P1-5374,188676892,5402,5404 P2-5401,5388 P3-188681673,188681694
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 11 issues 2.Tested Availability versus error and availability impact summary in new sunops. 3.Tested and delivered BOM feature in test and production Sunops |  | P1- 5377, 5389, 5403, 188676905, 188681761 P2- 5375, 5405, 188680975, 188680979 P3- 5390, 5408
| Week -51 | 16-12-2024 to 20-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 8 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure.
P1-5409,5410,5411,188703177 188703244 P2-5426,5427,5428,5412
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 5days) = 40 | 1.Validtaed the issue fixes. Validated 8 issues Filed 6 issues 2.Tested devices table in pinot after schedular has been rescheduled. 3.Tested tracker with error card and zones communicating feature 4.Tested SunDAT after migrating Jsapi,db api , tga api to azure. |  | P1- 5410, 5429, 5389, 5431 P2- 5414, 5430
| Week -52 | 23-12-2024 to 27-12-2024
Sl .No | Resource Name | Company Name | No. of Hrs / week | Deliverables/progress | No.of Test cases written/updated | Defect Details
1 | Brindha | SunDAT/ SunOPS | (8 hrsx 2days) = 16
2 | Rasikapriya | SunDAT/ SunOPS | (8hrs x 4days) = 36